## SCHEDULE
JOB NUMBER | JOB NAME | EQUIPMENT TYPE | SOLD TO | VALUE | P.O DATE | SCHLD SHIP | DIRECT LABOR HRS | SHOP DRWS RELEASED | PURCH | MECH DONE | FAB IN | FAB OUT | ASSY IN | ASSY OUT | QC | FAT | ADDITIONAL COMMENTS | ENG | W/D | SUBM | RESUB | APVL RECEIVED
|  |  | TOTAL | 223934
AUGUST 2018
51514C | DROUGHT RELIEF | BACK PNLS DOORS & RMA BKRS | ROYAL BAKERSFIELD | 632.16 | 2018-06-20 | 2018-08-27 | 5 | [9 empty] | RMA - BKRS STILL NEED TO SEND BACK
51560B 51560-5 | SO CAL GAS "PDR" | XFMR 5KV S/STL 3R SKID | ROYAL WHOLESALE | 59600 | 2018-02-28 | 2018-08-31 | 70 | 2018-06-26 | xfmr 7-6 | status?? |  | hrg & rly box 8-8 paint |  |  |  | WILL WANT | DONE - READY TO SHIP | ET 4/13 |  | ET 5-8 |  | 6-19
|  |  | TOTAL AUGUST: | 60232.16
SEPTEMBER 2018
51572-1 | LADWP MISSION WELLS IMPROVEMENT | N3R CLIMATE CONTROLLED NON-WALK-IN | ROYAL VERNON | 46451 | 2018-04-16 | 2018-09-07 | 150 | 2018-06-26 |  | 8-10 MZ | ansi 49 |  |  |  |  | 2018-09-11 | DONE - READY TO SHIP 9-21-18 | FA 4-27 |  | 2018-06-18 |  | 6-26-18
51490-1 | WASTEWATER FACILITY (HOBBS) | -15KV SWGEAR 3R "HVMDP' | EC POWER SYSTEMS COLORADO | 117395 | 9/25 | 8/15/2018 9-26-18 | 400 | 2018-05-29 | KK 9-24? | MZ 6-15, 6-27, 7-11, 7-13 | 7-10 START FAB | base paint 8-8 |  |  |  |  | 8-10 WEEKS FOR SUBMITTAL 16-18 WEEKS AFTER APPROVE |  |  | 11/13 |  | 5-24!
51560A 51561-1 51560-2 51560-8 51560-9 | SO CAL GAS "PDR" | S/STL IPC W/5KVMTR SWGEAR S/STL 5KV UGPS DC PNL AC PNL | ROYAL WHOLESALE | 440941 | 2018-02-28 | 2018-09-28 | 1200 | 2018-06-26 | bat due 10-5; HVAC COATED COILS? | mg | [6 empty] | 4-5-18 bom long lead released -1 SUB DUE 4-27; -2,-3 DUE 5-8; C/O RECEIVED 5-18; base done due 8-24 | ET 4/13 |  | ET 5-8 AM 6-1 |  | 6-19
|  |  | TOTAL SEPT: | 604787
OCTOBER 2018
51242-1 -2 | LUALUALEI LINE BOOSTERS | GEN TERMINATION CABINET N4X 316 800A MCC N12 | FLUID TECHNOLOGY | 102650 | 2016-10-19 | 2018-10-05 | 319 | 6/4/2018 7-18-18 | heat shrink | 8-22 MZ |  |  |  | Oct 1 | 10-5 | 2018-10-08 | 8-10wks lead; SHIP AFTER OCT 11,2018; | 11/23 1/24 |  | 11/23 1/24 | 3/28 DONE 9/9 DONE 10/3 | 6-4-18 Revised PO on 7-17-18
51664-1 -2 -3 -4 | MEDIFEE LAKES 2 PREMIUM | SES N3R MTR-MAIN & MULTI0MTR 3PACK | WALTERS - SAN DIMAS | 71976 | 2018-09-11 | 2018-10-05 | 220 | 9-19-18, rev 9-21-18 | boltswitch, siemens | [7 empty] | PREMIUM 2 weeks - changed from bkrs to switches on 9-18-18 | RS |  |  | 9-21-18 record only
51665-1 | US FARMS PREMIUM | 800A SES N3R APS | DYKMAN | 9228 | 2019-09-10 | 2018-10-08 | 25 | 2018-09-13 | ASCO APT | mz 9-19 | [6 empty] | PREMIUM 4WK ESPI | RS |  | 2018-09-13
51618-1 | Pismo Beach | 4X Wrap S/stl 304 | Wesco- Buena Park | 15981 | 2018-07-12 | 2018-10-09 | 70 | 2018-08-29 |  | 9-14 due | [6 empty] | subs 3-4 wks; ship 6-8 after delivery of FBO gear - Eaton arrived | RS |  | 8/2/2018 done |  | 8-28-18
51625-1 | ROCKWELL SWGR & IPC | ENGINEERING IPC & SWGEAR - DRAWINGS ONLY | BORDER STATES | 20000 | 2018-07-25 | 10/9/2018 ASKING 9-26-18 10-4-18 | 23 for dwgs only 202 + 855 | NA | NA | NA | NA | NA | NA | NA | NA | NA | SUBS 6 WKS after get Rockwell drawings complete; KICK OFF MTG 8-14; RA dwgs rec'd 9-11-18; REQUESTED 9-26-18 | AG |  | due 10-9
51647-1 | 16470 PROLOGIS | SES 4000A | AMERICAN ELECTRIC | 15316 | 2018-08-13 | 2018-10-08 | 60 | 2018-08-27 | done | 9-6 mz due | [6 empty] | 6-8 WEEK SHIP | RS |  | UTIL 8-27
51678-1 | AMERICAN 1ST CREDIT UNION | 125A PANEL | CED METRO | 584 | 2018-09-26 | 2018-10-15 | 2 | 2018-09-27 | [8 empty] | SHIPPED CAN 9-28-18
51579-1 | NEEDHAM RANCH | 800A 3R SWBRD SES MTR-MAIN | CED-ROYAL VENTURA | 9821 | 2018-05-03 | 2018-10-26 | 40 | 2018-09-13 | ASCO APT | MZ 10-5 | [6 empty] | KIRK KEY, 2 MAINS; 6 -8 wks | ET 5-17 |  | 2018-05-21 |  | 9-12-18
51635-1 | RESA LISW | DUPLEX LISW | RESA PWR | 18586 | 2018-08-06 | 2018-10-29 | 65 | 2018-09-11 |  | 9-28 NO! | [6 empty] | WILL CALL; DWGS 2WK, DEL 4 WKS; REVISED TO ADD SECTION; REVISE TO ADD KIRK KEYS | RS |  | 8-17 done | 8-24 done; 8-29 done
50963-1 | UL TEST SAMPLE | LV PWR CB | PIONEER |  |  | 2018-10-22 | 20 |  |  | 9/18 | 9/19 | 9/25 | 9/26 | 9/29 | 10/1
|  |  | TOTAL OCT: | 264142
NOVEMBER 2018
51669-1 | WHALEY PARK | 400A SES SPECIAL OHPS MTR-MAIN | WALTERS COMPTON | 6265 | 2018-09-14 | 2018-11-05 | 25 | 2018-09-24 | [8 empty] | SUBMIT TO UTILITY FIRST - approval rec'd |  |  | 9-24 DONE |  | 9-24-18
51653-1 | HEB 752 HUDSON OAKS | ATS 2500-2500-B3 | ERE | 71770 | 2018-08-30 | 2018-11-08 | 300 | [9 empty] | RELEASED MECHANICALLY 9-27-18; RESUB ELECTRICAL |  |  | 9-18 DONE | DUE 10/11 | 9-27
51649-1 | BROOKS & MONTE VISTA 18170 | 1200A SES 800A DIST | AMERICAN ELECTRIC | 7083 | 2018-08-23 | 2018-11-09 | 27 | 2018-08-27 | [8 empty] | IMMEDIATE RELEASE GREGG 18170-2S-7A |  |  | 8-27-18 RS
51682-1 | HANSEN | DIST BOARD 1800A | ROSEMEAD ELECTRIC | 17395 | 2018-09-28 | 2018-11-16 | 77 | [9 empty] | DWGS 2-4 WK, SHIP 6-8 WKS |  |  | due 10-9
51560C 51560-6 | SO CAL GAS "PDR" | XFMR & S/STL 480V NON-WALK-IN SKID | ROYAL WHOLESALE | 257900 | 2018-02-28 | 2018-11-20 | 700 | 2018-06-26 | XFMR 8-14 GE 8-24 | mg - need skid now | [6 empty] | 4-5-18 bom long lead released -1 SUB DUE 4-27; -2,-3 DUE 5-8; C/O RECEIVED 5-18 | ET 4/13 |  | ET 5-8 |  | 6-19
51577-1 | Building 310 | 3R WRAP 304 S/STL, ANSI 61 | FLUID TECHNOLOGY | 9308 | 2018-04-24 | 2018-11-21 | 36 | 2018-08-28 | [8 empty] | DWGS 4-6; BUILD 10-12 AFTER FBO : request ship 2-3 wks after FBO Siemens which should arrive 10-31-18 | RS 5-8 |  | 2018-05-09
51668-1 | 17470 CHERRY COMMERCE CENTER | 3000A SES 800A MTR-MAIN & DIST | AMERICAN ELECTRIC | 8884 | 2018-09-14 | 2018-11-21 | 30 | 2018-09-21 | [8 empty] | DELIVER MONDAY AFTER THANKSGIVING 17470-2S-7A |  |  | 9-21-18 RS
51676-1 | 17550 SYCAMORE CANYON | 4000A SES MTR-MAIN ONLY 2SEC | AMERICAN ELECTRIC | 6886 | 2018-09-20 | 2018-11-22 | 25 | 2018-09-24 | [8 empty] | DELIVER 11-26-18 |  |  | 9-24 DONE
51608-1 | WARREN E & P | 3R ENCLOSURE FOR VFD (NON-WALK-IN) | EATON | 58643 | 2018-06-27 | 2018-11-27 | 111 | 2018-09-12 | FBO 11-7 | MG WHEN SKID? | 2018-08-16 |  |  | 2018-11-15 | 11-19 | 2018-11-20 | subs 2-4, ship 10 wks, install vfd 2-3 after received; delivery 11-12-18 requested. 8-27-18 WANT DIFFERENT PLATFORM DESIGN - to give dwgs | ET |  | due 7-25 | 8/17/18 done; 8-24 DONE | 8-21-18
51671-1 | 18130 RUBBERMAID | 4000A SES, 1200A MTR-MAIN-DIST | AMERICAN ELECTRIC | 13995 | 2018-09-18 | 2018-11-28 | 40 | 2018-09-21 | [8 empty] | DELIVER MONDAY 12-3-18, MARK 18130-2S-7A VICTORVILLE |  |  | 9-21-18 RS
51655-1 -2 | CC BAKERY | GCB CABINETS | ERE | 46000 | 2018-08-30 | NOV | 250 | [12 empty] | DUE 9-28
51657-1 | TRADITIONS WOODWAY | ATS 3000-2500-B3-E1-SS1-C1-V3:LS600/600/250 | ERE | 84582 | 2018-08-31 | NOV | 300 | [9 empty] | DWGS 4-6 WKS, SHIP 6-8 WKS | ET |  | DUE 10-5
51616-1 -2 -3 -4 -5 | LAGUNA HOUSE | SES 304 N3R PANELS | ANTHONY WHSL | 44001 | 2018-07-06 | NOV | 100 | [9 empty] | SUBS 4-6, SHIP 6-8 | SAL,RS |  | 8-1 DONE | 9-21 DONE
|  |  | TOTAL NOV: | 632712
DECEMBER 2018
51575-1 -2 -3 -4 -5 -6 -7 -8 | P66 SFR REPLACE UNIT 200 SWITCHRACK F | IPC MVSG 2.5KV MV-MCC BUS DUCT XFMR 1000KVA LVSG 480V LV-MCC-A LV-MCC-B | PHILLIPS 66 | 1021533 | 2018-04-12 | 2018-12-27 | 1000 | BOMS RELEASED BUT DRAWINGS NOT YET | [8 empty] | EATON EQUIPMENT TO ORDER ASAP; SUBMITTALS DUE 2 WKS AFTER EATON BY 6-15; EATON 20 WEEK BUILD; LVSWGR SHIP TO PCEP 12-31; 2019 SHIP. LV SWGR TO SHIP FROM EATON ON 12-31-18 | FA 7-2 |  |  |  | 8-2-18 dwgs sent "release as noted" substantial revisions and corrections required - resub due 8-21
51646-1 -3 -5 | PEARL CITY WELLS II | 200HP STARTER 4X GEN TERM CAB (2)N4X RTU | FLUID TECHNOLOGY | 156342 | 2018-08-20 | DEC | 5 | [9 empty] | SITE VERIFICATION & ENG SERVICES | FA |  | DUE 9-21,reset due 9-28 | DUE 10-2
51670-1 | HANSEN STEEL | 4000A SES 3R | ROSEMEAD ELEC | 46609 | 2018-09-17 | DEC | 160 | [9 empty] | DWGS 2-4; SHIP 6-8 | RS |  | DUE 10-5
51683-1 | HEB 085 SA-41 SAN ANTONIO | ATS 3000-3000-B4 | ERE | 74460 | 2018-09-27 | DEC | 300 | [9 empty] | SUBS 4 WKS - TAKE 51674 PLACE IN ENG QUEUE | ET |  | DUE 10-18
51663-1 -2 -3 -4 | 17600 PACIFIC POINTE | 3000A SES N1 1200A MSW | AMERICAN ELECTRIC | 53973 | 2018-09-10 | DEC | 57 | [9 empty] | DWGS 2-4 WKS, SHIP 6-8; APPROVED FOR LONG LEAD ITEMS PURCHASED | RS |  | 9-24 DONE
51661-1 | PROJECT CHERRY | 12KV METALCLAD SWGEAR SCE SES | AMERICAN ELECTRIC | 115662 | 2018-09-06 | DEC | 350 |  | LONG LEAD AUTHORIZED - POWELL | [7 empty] | THIS IS A COPY OF 51559. GREGG ELECTRIC 18500-2S-7A | CG RS VALUE ADDED |  | 9-27 done
51372-1 -2 -3 -4 -5 | HALAWA WELLS | MCC & GAUGEBOARD WELL PUMP 3 WELL PUMP3 TEMP 600A CABINET | FLUID TECHNOLOGY | 210180 | 5/12 | DEC | 850 |  | RELEASE 7-12? | [7 empty] | STILL OUT FOR APPROVAL 10/12/17 ; SUBMITTAL RESPONSES DUE 5-21; 12-14 WKS BUILD | 6/13 6-15 |  | 6/13 6-15 DONE | DUE 5-21
51505-1 | SHOPRITE COUNTRY POINT 2017 | TYPE 3R NON WALK- IN 1 GENERATOR SWB 200A | UNSION | 40790 | 10/18 | DEC | 201 |  | RELEASE 8-8? | [7 empty] | SUBMITTALS DUE 2-3 WEEKS (EDGAR). Price to be updated. Release in Q3 2018, BUILD 8-12 WKS | 11/10 11/15 |  | 11/10 11/15 DONE
51617-1 -2 | RESI DENTIAL ENERGY STORAGE | RESI STAND ALONE BOARD MICRO-GRID | EOS ENERGY | 102972 | 2018-07-09 | DEC | 268 | [9 empty] | MEETING 9-12 W/ CLEMENS
51563-1 | INTEGRATED ENERGY SK | INTEGRATED ENERGY STORAGE SKID | EOS ENERGY | 57179 | 2018-03-08 | DEC | 293 | DESIGN REVIEW 7-12 | [7 empty] | 10-25 Clemens visit | 4 WEEKS SUBMITTAL due 5-29-18 ORDER released from Hold, CUST VISIT 7-12; DWGS TO PCEP 6-29 7-12-18 CLEMENS TO CREATE NEW DROP BOX FOR DRAWINGS | FA & LIN |  | NEED DROP BOX & eos dwgs | DUE 10-19
|  |  | TOTAL DEC: | 1879700
2019 SHIPMENTS
JANUARY 2019
51666-1 | 18630 RANCHO CUCAMONGA | 800A SESSCE + DIST | AMERICAN ELECTRIC | 6488 | 2018-09-12 | 2019-01-09 | 25 | 2018-09-25 | [8 empty] | 18630-2S-5A
51644-1 -2 | PUNALUU WELLS / HECO | 5KV SES MTR-MAIN NWI 3R TEMP 5KV N1 HECO | FLUID TECHNOLOGY | 71690 | 2018-08-17 | JAN | 164 | [10 empty] | AG |  | DUE 9-14 done 9-17 | DONE 9-28
51681-1 | OHAI MCC WRAP | S/STL 3R WRAP PAINTED ANSI 61 | FLUID TECHNOLOGY | 20790 | 2018-09-27 | JAN | 78 | [12 empty] | DUE 10-28
51592C-1 -2 | BLH#3 | SUBSTATION #1 SUBSTATION #2 | BLH#3 | 361613 | 2018-07-23 | JAN | 1400 | [9 empty] | PROGRESS BILLINGS, subs 8-10 weeks, ship 26-28 weeks O&M only electronic |  |  | CG 8-7 | CG 8-13 done DONE 9-28
51573-1 | HYPERION WRP IPS ODOR CONTROL | IPC | WALTERS - SAN DIMAS | 85551 | 2018-04-18 | JAN | 146 |  | RELEASE JUNE 30? | [7 empty] | DWGS (4-6WKS) 14-16 WKS; RADCO APPROVAL RECEIVED | AM & JA & FA 5-18 |  |  | ja due 6-20
51598-1 -2 -3 -4 -5 -6 -7 --8 SPARE | REPLACE BUS A STATION B NAVFAC S633 | 15KV NEW SWGR 15KV TEMP SWGR 15KV BKRS NEW DOORS NEW DOORS NEW DOOR NEW DOOR NEW DOOR SPARE PARTS | FLUID TECHNOLOGY | 407963 | 2018-06-08 | JAN | 592 144 0 15 15 15 15 15 15 | [9 empty] | REQUEST SUBMITTALS 7-13 | et 7-9 |  | 7-13 done | DONE 7-23
|  |  | TOTAL JAN: | 954095
FEBRUARY 2019
51490-2 -3 -4 -5 | WASTEWATER FACILITY (HOBBS) | -IPC -SWBD -CONTROL SECTION PLC PANEL PANELBOARD | EC POWER SYSTEMS COLORADO | 352185 | 9/25 | FEB | 380 40 150 40 20 |  | RELEASE JUNE 30? | RELEASE SWGR | [6 empty] | 8-10 WEEKS FOR SUBMITTAL 16-18 WEEKS AFTER APPROVE |  |  | 11/13 | DUE 5-31
51490-3 | HOBBS | PLC EG1-CP CONTROL PANEL | EC CONTROLS |  |  | FEB | 40 | 2018-09-20 | [8 empty] | SHIP 18-20 WKS? CAN THIS BE PULLED IN?
51677-1 | P66 MCKITTRICK | IPC | P66 | 434383 | 2018-09-21 | FEB | 1200 | [9 empty] | PROGRESS BILLINGS; DWGS 6 WKS, SHIP 16 WKS |  |  | DUE 11-2-18
|  |  | TOTAL FEB: | 786568
MARCH 2019
51592-1 -2 | BLH#3 | UTY MSVG 15KV SWGEAR TYPE 1 | BLH#3 | 777162 | 2018-05-30 | MAR | 2000 | KICK OFF MTG 1PM 6-11 | [8 empty] | JOB# 16-845-82; MORE PO TO FOLLOW; SUBS 8-10 WKS; SHIP 26 WEEKS | fa | NO | CG 8-7 | CG 8-13 done DONE 9-28
51592B-1 -2 -3 | BLH#3 | 15KV MVSG-1 MASTER CNTL#1 MASTER CNTL #2 | BLH#3 | 1141900 | 2018-06-08 | MAR | 550 | KICK OFF MTG 1PM 6-11 | [8 empty] | PROGRESS BILLINGS, subs 8-10 weeks, ship 26 weeks O&M only electronic | FA | NO | CG 8-7 | CG 8-13 done DONE 9-28
51555-3 | FORT SHAFTER | (1) 15KV LI SWICH SS 304 | FLUID TECHNOLOGY | 420330 | 2018-02-12 | MAR | 73 | [9 empty] | SUBMITTALS NEED TO BE DONE BY MARCH 23RD RELEASE EATON MAT'L 10-22-18 (previous price listed was entire job) | 3/23 |  | FA 3/23 | 4-24 due 8-23
|  |  | TOTAL MARCH: | 2339392
MAY 2019
51555-2 | FORT SHAFTER | (1) 15KV LI SWICH SS 304 | FLUID TECHNOLOGY | 485390 | 2018-02-12 | MAY | 73 | [9 empty] | SUBMITTALS NEED TO BE DONE BY MARCH 23RD RELEASE EATON 9-10-18 | 3/23 |  | FA 3/23 | 4-24; due 8-23
JUNE 2019
51555-1 -4 -5 | FORT SHAFTER | (1) 15KV LI SWICH SS 304 POWELL 15KV (3) ABB 1200A (4) | FLUID TECHNOLOGY | 511131 | 2018-02-12 | JUN | 113 | [9 empty] | SUBMITTALS NEED TO BE DONE BY MARCH 23RD RELEASE EATON 8-6-18 | 3/23 |  | FA 3/23 | 4-24 DUE 8-23 AG Due 9-4
IN PROCESS
51658-1 | SHOPRITE RONKONKOMA | GENERATOR SWBRD DRAWINGS ONLY | UNISON ENERGY | 2095 | 2018-09-05 | ON HOLD | 30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | THIS PO FOR ENGINEERING SUBMITTAL DRAWINGS ONLY 3 WKS LEAD TIME; ON HOLD 9-11-18
51677-1 | P66 MCKITTRICK | IPC | P66 |  | 2018-09-21 | FEB | 1200 | [9 empty] | PROGRESS BILLINGS; DWGS 6 WKS, SHIP 16 WKS |  |  | DUE 11-2-18
51646-1 -3 -5 | PEARL CITY WELLS II | 200HP STARTER 4X GEN TERM CAB (2)N4X RTU | FLUID TECHNOLOGY |  | 2018-08-20 | DEC | 5 | [9 empty] | SITE VERIFICATION & ENG SERVICES | FA |  | DUE 9-21,reset due 9-28 | DUE 10-2
51655-1 -2 | CC BAKERY | GCB CABINETS | ERE |  | 2018-08-30 | NOV | 250 | [12 empty] | DUE 9-28
51670-1 | HANSEN STEEL | 4000A SES 3R | ROSEMEAD ELEC |  | 2018-09-17 | DEC | 160 | [9 empty] | DWGS 2-4; SHIP 6-8 | RS |  | DUE 10-5
51657-1 | TRADITIONS WOODWAY | ATS 3000-2500-B3-E1-SS1-C1-V3:LS600/600/250 | ERE |  | 2018-08-31 | NOV | 300 | [9 empty] | DWGS 4-6 WKS, SHIP 6-8 WKS | ET |  | DUE 10-5
51683-1 | HEB 085 SA-41 SAN ANTONIO | ATS 3000-3000-B4 | ERE |  | 2018-09-27 | DEC | 300 | [9 empty] | SUBS 4 WKS - TAKE 51674 PLACE IN ENG QUEUE | ET |  | DUE 10-18
51680-1 | RAMPART METHANE | UGPS (2) | ONE SOURCE VAN NUYS | 2323 | 2018-09-27 |  | 10 | [10 empty] | RS |  | DUE 10-18
51681-1 | OHAI MCC WRAP | S/STL 3R WRAP PAINTED ANSI 61 | FLUID TECHNOLOGY |  | 2018-09-27 | JAN | 78 | [12 empty] | DUE 10-28
51563-1 | INTEGRATED ENERGY SK | INTEGRATED ENERGY STORAGE SKID | EOS ENERGY |  | 2018-03-08 | DEC | 293 | DESIGN REVIEW 7-12 | [7 empty] | 10-25 Clemens visit | 4 WEEKS SUBMITTAL due 5-29-18 ORDER released from Hold, CUST VISIT 7-12; DWGS TO PCEP 6-29 7-12-18 CLEMENS TO CREATE NEW DROP BOX FOR DRAWINGS | FA & LIN |  | NEED DROP BOX & eos dwgs | DUE 10-19
51644-1 -2 | PUNALUU WELLS / HECO | 5KV SES MTR-MAIN NWI 3R TEMP 5KV N1 HECO | FLUID TECHNOLOGY |  | 2018-08-17 | JAN | 164 | [10 empty] | AG |  | DUE 9-14 done 9-17 | DONE 9-28
51592-1 -2 | BLH#3 | UTY MSVG 15KV SWGEAR TYPE 1 | BLH#3 |  | 2018-05-30 | MAR | 2000 | KICK OFF MTG 1PM 6-11 | [8 empty] | JOB# 16-845-82; MORE PO TO FOLLOW; SUBS 8-10 WKS; SHIP 26 WEEKS | fa | NO | CG 8-7 | CG 8-13 done DONE 9-28
51592B-1 -2 -3 | BLH#3 | 15KV MVSG-1 MASTER CNTL#1 MASTER CNTL #2 | BLH#3 |  | 2018-06-08 | MAR | 550 | KICK OFF MTG 1PM 6-11 | [8 empty] | PROGRESS BILLINGS, subs 8-10 weeks, ship 26 weeks O&M only electronic | FA | NO | CG 8-7 | CG 8-13 done DONE 9-28
51592C-1 -2 | BLH#3 | SUBSTATION #1 SUBSTATION #2 | BLH#3 |  | 2018-07-23 | JAN | 1400 | [9 empty] | PROGRESS BILLINGS, subs 8-10 weeks, ship 26-28 weeks O&M only electronic |  |  | CG 8-7 | CG 8-13 done DONE 9-28
51663-1 -2 -3 -4 | 17600 PACIFIC POINTE | 3000A SES N1 1200A MSW | AMERICAN ELECTRIC |  | 2018-09-10 | DEC | 57 | [9 empty] | DWGS 2-4 WKS, SHIP 6-8; APPROVED FOR LONG LEAD ITEMS PURCHASED | RS |  | 9-24 DONE
51661-1 | PROJECT CHERRY | 12KV METALCLAD SWGEAR SCE SES | AMERICAN ELECTRIC |  | 2018-09-06 | DEC | 350 |  | LONG LEAD AUTHORIZED - POWELL | [7 empty] | THIS IS A COPY OF 51559. GREGG ELECTRIC 18500-2S-7A | CG RS VALUE ADDED |  | 9-27 done
51659-1 | C-3160 SCE MEER | N12 CABINET DUAL DOORS | FACILITIES PROTECTION SYSTEMS | 3828 | 2018-09-06 |  | 8 | [9 empty] | THIS IS NOT A HOUSE, IT IS ONLY A CABINET |  |  | done 9-27
51636-1 | HART PEARL MSA SWBRD | 3R WRAP 304 S/STL POWDER COATED ANSI 61 | FLUIDTECH | 4950 | 2018-08-06 |  | 18 | NOT | [9 empty] | RS SENT DWG TO FLUID 8-8-18
51574-1 51574-2 | REPLACE SEWAGE | N3R 316 WRAP MCC N3R 316 WRAP ATS | FLUID TECHNOLOGY | 19600 |  |  | 50 | NOT | RELEASE 6-20? | [7 empty] | 10-12 WKS BUILD; DEPENDS WHEN GET FBO, NEED 6 WEEKS | RS 5-11 |  | 5-8 done
51467-1 | NEMA 4 ENCLOSURES | NEMA 4 ENCLOUSURES (3) | GDS INDUSTRIES | 15462 | 8/23 |  | 135 | NOT | RELEASE 6-27? | [7 empty] | 8 - 10 BUILD AFTER APPROVAL | 9/11 |  | 9/11 DONE
51582-1 | NEMA 4 ENCLOSURES | NEMA 4 ENCLOUSURES (8) | GDS INDUSTRIES | 41232 | 2018-05-04 |  | 13 | NOT | RELEASE 6-27? | [7 empty] | SAME AS 51467-1; 8-10 WKS | 5-25 |  | 5/25 DONE
51573-1 | HYPERION WRP IPS ODOR CONTROL | IPC | WALTERS - SAN DIMAS |  | 2018-04-18 | JAN | 146 | WHY NOT | RELEASE JUNE 30? | [7 empty] | DWGS (4-6WKS) 14-16 WKS; RADCO APPROVAL RECEIVED | AM & JA & FA 5-18 |  |  | ja due 6-20
51372-1 -2 -3 -4 -5 | HALAWA WELLS | MCC & GAUGEBOARD WELL PUMP 3 WELL PUMP3 TEMP 600A CABINET | FLUID TECHNOLOGY |  | 5/12 | DEC | 850 | NOT | RELEASE 7-12? | [7 empty] | STILL OUT FOR APPROVAL 10/12/17 ; SUBMITTAL RESPONSES DUE 5-21; 12-14 WKS BUILD | 6/13 6-15 |  | 6/13 6-15 DONE | DUE 5-21
51490-2 -3 -4 -5 | WASTEWATER FACILITY (HOBBS) | -IPC -SWBD -CONTROL SECTION PLC PANEL PANELBOARD | EC POWER SYSTEMS COLORADO |  | 9/25 | FEB | 380 40 150 40 20 | NOT | RELEASE JUNE 30? | RELEASE SWGR | [6 empty] | 8-10 WEEKS FOR SUBMITTAL 16-18 WEEKS AFTER APPROVE |  |  | 11/13 | DUE 5-31
51505-1 | SHOPRITE COUNTRY POINT 2017 | TYPE 3R NON WALK- IN 1 GENERATOR SWB 200A | UNSION |  | 10/18 | DEC | 201 |  | RELEASE 8-8? | [7 empty] | SUBMITTALS DUE 2-3 WEEKS (EDGAR). Price to be updated. Release in Q3 2018, BUILD 8-12 WKS | 11/10 11/15 |  | 11/10 11/15 DONE
51617-1 -2 | RESI DENTIAL ENERGY STORAGE | RESI STAND ALONE BOARD MICRO-GRID | EOS ENERGY |  | 2018-07-09 | DEC | 268 | [9 empty] | MEETING 9-12 W/ CLEMENS
51629-1 | PUNALUU WELLS II | 4X 316 GEN TERM CAB | FLUID TECHNOLOGY | 27303 | 2018-07-27 |  | 15 | [9 empty] | DIRECT COPY OF 51308-3 AS BUILT = NOT!! | FA |  | DUE 8-10 | 8-28-18 DONE
51555-1 -4 -5 | FORT SHAFTER | (1) 15KV LI SWICH SS 304 POWELL 15KV (3) ABB 1200A (4) | FLUID TECHNOLOGY |  | 2018-02-12 | JUN | 113 | NOT | [8 empty] | SUBMITTALS NEED TO BE DONE BY MARCH 23RD RELEASE EATON 8-6-18 | 3/23 |  | FA 3/23 | 4-24 DUE 8-23 AG Due 9-4
51555-2 | FORT SHAFTER | (1) 15KV LI SWICH SS 304 | FLUID TECHNOLOGY |  | 2018-02-12 | MAY | 73 | NOT | [8 empty] | SUBMITTALS NEED TO BE DONE BY MARCH 23RD RELEASE EATON 9-10-18 | 3/23 |  | FA 3/23 | 4-24; due 8-23
51555-3 | FORT SHAFTER | (1) 15KV LI SWICH SS 304 | FLUID TECHNOLOGY |  | 2018-02-12 | MAR | 73 | NOT | [8 empty] | SUBMITTALS NEED TO BE DONE BY MARCH 23RD RELEASE EATON MAT'L 10-22-18 (previous price listed was entire job) | 3/23 |  | FA 3/23 | 4-24 due 8-23
51616-1 -2 -3 -4 -5 | LAGUNA HOUSE | SES 304 N3R PANELS | ANTHONY WHSL |  | 2018-07-06 | NOV | 100 | [9 empty] | SUBS 4-6, SHIP 6-8 | SAL,RS |  | 8-1 DONE | 9-21 DONE
51603-1 | PUNALUU WELLS | 400A Dist swbrd 3R 316 S/stl gaugeboard 3R line-up | FLUID TECHNOLOGY | 45100 | 2018-06-18 |  | 100 | [9 empty] | subs 4-6, due 7-20-18; ship 8-10 wks | et 7-16 |  | done 7-20 | 7-25 DONE
51609-1 | c2f enclosure my | non-walk-in 3R 304 wrap | FLUID TECHNOLOGY | 19895 | 2018-06-26 |  | 70 | [9 empty] | subs due 7-27; ship 6-8 wks | AG |  | done 7-23 | 7-26 DONE
51598-1 -2 -3 -4 -5 -6 -7 --8 SPARE | REPLACE BUS A STATION B NAVFAC S633 | 15KV NEW SWGR 15KV TEMP SWGR 15KV BKRS NEW DOORS NEW DOORS NEW DOOR NEW DOOR NEW DOOR SPARE PARTS | FLUID TECHNOLOGY |  | 2018-06-08 | JAN | 592 144 0 15 15 15 15 15 15 | [9 empty] | REQUEST SUBMITTALS 7-13 | et 7-9 |  | 7-13 done | DONE 7-23
51519-1 -3 | REGIMENTAL CONSOLIDATION FACILITY | GROUND BAR ASSY GROUNDING CABINETS | FLUID TECHNOLOGY | 9630 | 2017-11-30 |  | 20 | NOT | [9 empty] | 12/8 |  | 12/8 DONE | 1/31 2/9 DONE
51436-1 | WAIKALUA WWTTP | NEMA 4X WALL TERMINAL CABINET | FLUID TECHNOLOGY | 4000 | 8/6 |  | 40 | NOT | [8 empty] | STILL OUT FOR APPROVAL 10/12/17 | 8/18 |  | 8/18 DONE
51429-1 | KAHANAHOU | NEMA 4X | FLUID TECHNOLOGY | 4800 | 7/27 |  | 40 | NOT | [8 empty] | STILL OUT FOR APPROVAL 10/12/17 | 8/18 |  | 8/18 DONE
51379-1 | BOB HOPE AIRPORT | NEMA 3R OUTDOOR | ROYAL INDUSTRIAL | 28600 | 6/5/17 |  | 130 | NOT | [8 empty] | SUBMITTAL DATE 6-23 (SEAN) DONE | 6/16 |  | 6/16 DONE | 6/26 DONE
50905-1 | HAWAII FIT 32 | COMMUNICATION CABINET | FLUID TECHNOLOGY | 28750 | 3/21/16 |  | 120 | NOT | [8 empty] | NO UPDATE MIGHT BE CANCELLED OR DELAYED 10/12/17 | 4/8/2016 |  | 4/8/2016 DONE
50904-1 | HAWAII FIT 32 | 800A N3R | FLUID TECHNOLOGY | 32805 | 3/21/16 |  | 120 | NOT | [8 empty] | NO UPDATE MIGHT BE CANCELLED OR DELAYED 10/12/17 | 4/8/2016 |  | 4/8/2016 DONE
51247-1 | LUALUALEI BOOSTER | ENCLOSED CB 4X 316 250A | FLUID TECHNOLOGY | 4850 | 10/25/16 |  | 20 | NOT | [8 empty] | STILL OUT FOR APPROVAL 10/12/17 | 11/18/2016 |  | 11/18/2016 DONE
|  |  | TOTAL IN PROGRESS: | 295223
COMPLETED ORDERS
51341-1 | SAGANING | IPC-MV SWGR | SAGINAW CHIPPEWA UTILITY | 630829 | 2-28-2017 | 11/22 12/29 2/27 | 2922 | 2017-08-30 | DONE | AM DONE MG DONE 11/02 |  |  |  |  | 2/9 | 2018-02-15 | WE CAN SHIP NOW!! 9-20-18 POSSIBLE 4 WKS FOR PERMITS |  |  | 4/28 5/3 DONE |  | 42935
51564-1 | LOS HERMANAS | 600A SWBD AL | AMERICAN ELECTRIC | 5074 | 2018-03-13 | 2018-04-19 | 18 | 2018-04-05 | IN STOCK | [7 empty] | DONE - BILL & HOLD |  |  | RS 3/22 DONE |  | 43195

## SHIPPED
JOB NUMBER | JOB NAME | EQUIPMENT TYPE | SOLD TO | VALUE | P.O DATE | SCHLD SHIP | DIRECT LABOR HRS | SHOP DRWS RELEASED | PURCH | MECH DONE | FAB IN | FAB OUT | ASSY IN | ASSY OUT | QC | FAT | ADDITIONAL COMMENTS | ENG | W/D | SUBM | RESUB | APVL RECEIVED
51010-1 | B L Harbert Intl | 4000 UL1558 swibd | B L Harbert Intl |  |  | 2017-03-10 | [10 empty] | MISSING O&M
51010-2 | B L Harbert Intl | 2000 UL1558 swibd | B L Harbert Intl | 34710 |  | 2/28 3/10 | [10 empty] | MISSING O&M
51010-3 | B L Harbert Intl | 3000 UL1558 swibd | B L Harbert Intl | 171954 |  | 2/28 3/10 | [10 empty] | MISSING O&M
51215-1 | Chief Joseph Commons | NEMA 3R SWBD | Cresent Electric | 23,996 | 3/7 | 2017-04-13 | [15 empty] | 3/20
51257-1 | MONSTER RIALTO | PANELS | WALTERS WHOLESALE | 30,000 | 11/1/16 | 4/13 | [10 empty] | MISSING BREAKER AND RATING PLUG
50818-1 | WEYMOUTH TREATMENT PLANT | IPC | EATON | 118238 | 2017-09-12 | 2017-04-13 |  | DONE |  | 3/13 | [6 empty] | special color: GRAY 49 Customer wants on site in April but MCC not due until 3-15, they told ship 6 weeks after receive MCC which would be 4-26-17 |  | DONE
51426-1 | GARDENA | 1000A SWBD | WALTERS WHOLESALE | 9875 | 7/26 | [11 empty] | JOB WAS CANCELED |  |  | 7/14 DONE
OCTOBER
51217-1 | ELLSWORTH | IPC-MV SWGR | BSE | 1041851 | 2016-09-29 | 2017-10-03 |  |  |  | DONE |  |  |  |  | 9/20 | 9/25 | 100% INVOICED
51493-1 | NEWLIGHT TECH | PANEL | WESCO | 1275 | 9/28 | 2017-10-05 | [10 empty] | ***PREMIUM***
51413-1 | STORE # 069 SPID/ WALDRON | LV ATS SWGR | ENCHANTED | 62052 | 7/18 | 2017-10-06 |  | 9/15 |  | AM DONE
51085-29 | STORE # 724 ALIANA | LV ATS SWGR | ENCHANTED | 54801 | 7/5/16 | 2017-10-06 |  |  |  | AM DONE
51085-45 | DALLAS STANDARD MEAT | LV ATS SWGR | ENCHANTED | 62984 | 7/5/16 | 2017-10-11 | 127 |  |  | AM DONE
51085-17 | STORE # 109 BUNKER HILL | LV ATS SWGR | ENCHANTED | 69501 | 7/5/2016 | 2017-10-11 | 130 |  |  | AM DONE
51085-18 | STORE # 596 GRAND PARKWAY | LV ATS SWGR | ENCHANTED | 59501 | 7/5/16 | 2017-10-13 | 130 | 2017-08-24 |  | AM DONE | 8/25 | [5 empty] | REWORK ON BAKER CYPRESS P.O RECEIVED |  | 8/24 | 8/24
51085-42 | STORE # 558 FRIENDSWOOD | LV ATS SWGR | ENCHANTED | 62214 | 7/5/16 | 2017-10-13 | 127 | 2017-08-30 |  | AM DONE | 8/30 | [7 empty] | 8/30 | 2017-08-29
51500-1 | 600A PNL | PANEL | WALTERS WHOLESALE | 1304 | 10/9 | 2017-10-18 |  | 2017-10-10 | [8 empty] | ***PREMIUM ***** DONE
51439-1 | SENERGY | DIST SWBD 100KA TIN PLATED BUS | TURTLE AND HUGHES | 10560 | 8/9 | [11 empty] | JOB WAS CANCELED |  |  | 8/22 DONE
51400-1 -2 -5 | MACY'S BLDG | NEMA 1 SES | WALTERS WHOLESALE | 26339 | 6/29 | 2017-10-17 | 100 | 8/28 |  | TA 9/4 DONE | 9/5 | 9/19 | 9/20 | 10/5 | 10/6 |  | SHIPPING -1 -2 -5 51400-3 AND 51400-4 ARE ON HOLD |  |  | SS 7/17 DONE
51506-1 | BGI | PANEL | AAA ELECTRICAL SUPPLY | 1494 | 10/19 | 2017-10-20 |  | 2017-10-19 | [8 empty] | PREMIUM
51415-1 | STORE # 139 WEBER/HOLLY | LV ATS SWGR | ENCHANTED | 55186 | 2017-07-18 | 2017-10-20 | 124 |  |  | AM/LF DONE
51473-1 -2 | JERSEY MIKES | PANELS | C.E.D PASADENA | 2010 | 9/15 | 10/9 10/18 | 8 | 9/21 |  | N/A | [6 empty] | PANEL "B" 51473-2 IS COMPLETE MISSING B340H00S01 | N/A | N/A | N/A | N/A | 9/21
51424-1 | HOLLY HALL | LV ATS SWGR | ENCHANTED | 63892 | 2017-07-26 | 2017-10-20 | 127 |  |  | 8/31 DONE | [6 empty] | CUSTOMER WOULD LIKE TO HAVE THIS JOB BEFORE 10/20
51498-1 | PACIFIC IND BANDINI | 4000A SES 4 SEC | AMERICAN ELECTRIC | 18975.6 | 10/9 | 2017-10-20 | 80 | 2017-09-25 |  | MZ DONE 10/10 | 10/2 | 10/6 | 10/9 | 10/13 | 10/16 |  | ***PREMIUM****
51489-1 | AGUA MANSA | 800A SES & DIST SEC | AMERICAN ELECTRIC | 9670.5 | 9/22 | 2017-10-18 | 40 | 2017-09-25 | 9/25 | 9/29 | 10/2 | 10/6 | 10/9 | 10/13 | 10/16 |  | DONE CUSTOMER NOTIFIED | 2017-09-23 | N/A | 2017-09-25 | N/A | 2017-09-25
51488-1 | RIDGE FONTANA | 4000A DIST SEC | AMERICAN ELECTRIC | 6450.3 | 9/22 | 2017-10-19 | 40 | 2017-09-25 | 9/25 | 9/29 | 10/2 | 10/6 | 10/9 | 10/13 | 10/16 |  | DONE CUSTOMER NOTIFIED |  |  | 2017-09-25 | N/A | 2017-09-25
51469-1 | CITRUS COMMERCE | 1600A DIST SEC | AMERICAN ELECTRIC | 6480 | 8/29 | 2017-10-24 | 40 | 2017-09-07 |  | 9/15 DONE | 9/22 | 10/6 | 10/9 | 10/20 | 10/23 |  | DONE CUSTOMER NOTIFIED 10/16
51431-1 | MERIDIAN II DIST | 4000A SES 3 SEC | AMERICAN ELECTRIC | 16425 | 7/28 | 2017-10-17 | 120 | 2017-08-14 |  | 8/16 DONE | 8/31 | 8/19 | 9/20 | 10/12 | 10/13 |  | DONE
51368-1 | STORE # 707 LACK JACKSON | LV ATS SWGR | ENCHANTED | 65204 | 5/2 | 2017-10-20 | 127 |  |  | AM DONE 8/23
51428-1 | BRITTEN STUDIOS | FIELD SERVICE EVALUATION | WINDEMULLER | 1600 | 7/26 | 2017-11-10 | [10 empty] | RALPH WILL PROCEED AFTER BLH
50513-1 | FORT SHAFTER | N4X WRAP N4X WRAP | SCHNEIDER ELECTRIC | 26725 | 8/17/2015 |  | 110 | [9 empty] | 5/16/16 LAST RESPONSE FROM CUSTOMER EMAILED CUSTOMER 10/16 EMAILS/ PHONES ARE NO LONGER IN SERVICE JOB WAS CANCELLED |  |  | 2015-12-02
51191-1 | PION UTILITY SWGR | METAL ENCLOSED UTILITY | ARIZONA ELECTRIC SUPPPLY | 39385 | 9/13/16 |  | 120 | [9 empty] | JOB WAS CANCELLED ON 4/20 |  |  | 2017-09-27
51292-1 | WALDORF MANOR | 1600A SES | C.E.D BEAUMOUNT | 8580 | 12/21/16 |  | 20 | [12 empty] | 2016-12-22
NOVEMBER
51085-31 | STORE #648 MI TIENDA 02 | LV ATS SWGR | ENCHANTED | 63764 | 7/5/16 | 2017-11-03 | 127 |  |  | DONE 8/30
51085-20 | STORE # 498 ATASCOCITA | LV ATS SWGR | ENCHANTED | 62214 | 2017-07-05 | 2017-11-03 | 127 | 10/06 |  | AM DONE 9/12
51387-1 | STORE # 721 KILLEEN 02 | LV ATS SWGR | ENCHANTED | 60937 | 2017-07-05 | 2017-11-03 | 127 |  |  | DONE |  |  |  |  | 10/23
51416-1 | STORE # 210 AKAMENDA/ ROBERTS | LV ATS SWGR | ENCHANTED | 55186 | 2017-07-18 | 2017-11-03 | 124 |  |  | DONE
51411-1 | REPLACE PRIMARY DIGESTER | 3R WRAP | FLUID TECHNOLOGY | 9875 | 7/3 | 10/27 11/3 | 40 | 9/25 |  | LF 10/9 | 10/10 | 10/17 | 10/18 | 10/25 | 10/26 |  | MCC ARRIVED 10/3 |  |  | 7/14 DONE |  | 9/21
51031-1 | V5616 | 450A N1 SECTION | VIRDI POWER | 6659 | 6/7/16 |  | 40 | [12 empty] | 11/6/7
50918-1 | NCMT BERTH 24-10 | 1000A SES | GEXPRO | 19295 | 3/29/16 |  | 80 | [9 empty] | JOB WAS CANCELLED ON 11/12 |  |  | 2016-06-21
51187-1 | VENICE BEACH | 1200A 208/120VAC | VF | 15473 | 9/12/2016 |  | 40 | [9 empty] | JOB WAS CANCELLED ON 07/26 |  |  | 2016-10-07
51419-1 | STORE # 270 SPID/ STAPLES | LV ATS SWGR | ENCHANTED | 55186 | 7/18/17 | 11/3 11/10 | 124 | 2017-10-24 |  | AM DONE 9/11
51085-30 | STORE # 720 KINGWOOD | LV ATS SWGR | ENCHANTED | 63764 | 7/5/16 | 10/27 11/10 | 127 |  |  | AM DONE 8/24 | [6 empty] | MISSING 3000A BREAKER TRIP UNITS ARRIVED 11-3-17
51085-43 | STORE # 615 PINE OAK | LV ATS SWGR | ENCHANTED | 63764 | 2016-07-05 | 2017-11-03 | 127 | [9 empty] | MISSING 3000A BREAKER TRIP UNITS ARRIVED 11-3-17
51508-1 | DRY DOCK | PANEL | FLUID TECHNOLOGY | 2653 | 10/25 | 2017-11-22 |  | 2017-10-31
51449-1 | STORE #20 BAKER CYPRESS | LV ATS SWGR | ENCHANTED | 24867 | 8/16 | 10/27 11/10 11/17 | 130 |  |  | DONE | [6 empty] | WAITING ON DSL FILE
51085-27 | STORE # 540 GILFGATE H42 | LV ATS SWGR | ENCHANTED | 63764 | 2017-07-26 | 10/30 11/10 11/17 | 127 |  |  | DONE
51421-1 | STORE # 462 CORPUS CHRISTI 02 | LV ATS SWGR | ENCHANTED | 60937 | 7/18/17 | 11/3 11/10 11/17 | 127 | 2017-10-31 |  | AM DONE 8/31
51400A-1 | MACY'S BLDG | PANEL | WALTERS WHOLESALE | 1693 | 6/29 | 2017-12-06 | 100 | [9 empty] | PANEL ADDED TO 51400 CUSTOMER WILL CALL CANS |  |  | 11/6
51400-4 -6 | MACY'S BLDG | PANELS | WALTERS WHOLESALE | 2082 | 6/29 | 2017-12-06 | 100 | [9 empty] | NEED TO REVISE PANELS CUSTOMER WILL CALL CANS |  |  | 11/6
51435-1 | TOYOTA OF TORRANCE | 5KV 1200A METAL CLAD | ONE SOURCE | 89537 | 8/4 | 2017-11-29 | 280 | 9/8 |  | AM 9/29 | 10/2 | 10/23 | 10/24 | 11/21 | 11/22 |  | BREAKERS ARE DUE 10/27 |  |  | 8/22 DONE | 8/31 DONE
51476-1 | TEXAS A&M | GCB PANEL | ERE | 22975 | 9/18 | 2017-11-28 | 63 | 2017-10-24 |  | 10/31 DONE | 11/1 | 11/13 | 11/14 | 11/23 | 11/24 |  |  |  |  | 2017-10-06 | 2017-10-16 | 2017-10-23
51477-1 | TEXAS A&M | GCB PANEL | ERE | 22975 | 9/18 | 2017-11-28 | 63 | 2017-10-24 |  | 10/31 DONE | 11/1 | 11/13 | 11/14 | 11/23 | 11/24 |  |  |  |  | 2017-10-06 | 2017-10-16 | 2017-10-23
51478-1 | TEXAS A&M | GCB PANEL | ERE | 22975 | 9/18 | 2017-11-28 | 63 | 2017-10-24 |  | 10/31 DONE | 11/1 | 11/13 | 11/14 | 11/23 | 11/24 |  |  |  |  | 2017-10-06 | 2017-10-16 | 2017-10-23
51479-1 | TEXAS A&M | GCB PANEL | ERE | 22975 | 9/18 | 2017-11-28 | 63 | 2017-10-24 |  | 10/31 DONE | 11/1 | 11/13 | 11/14 | 11/23 | 11/24 |  |  |  |  | 2017-10-06 | 2017-10-16 | 2017-10-23
51480-1 | TEXAS A&M | GCB PANEL | ERE | 22975 | 9/18 | 2017-11-28 | 63 | 2017-10-24 |  | 10/31 DONE | 11/1 | 11/13 | 11/14 | 11/23 | 11/24 |  |  |  |  | 2017-10-06 | 2017-10-16 | 2017-10-23
51417-1 | STORE # 212 MCALLEN 04 | LV ATS SWGR | ERE | 54076 | 7/18/17 | 11/10 11/17 11/28 | 124 | 2017-10-31 |  | DONE
51414-1 | STORE # 136 HARLINGEN 04 | LV ATS SWGR | ERE | 60937 | 2017-07-18 | 11/3 11/10 11/17 11/28 | 124 | 2017-10-27 |  | DONE | [6 empty] | SCHDULE TO SHIP 11/27
51375-1 | EL PASO ELECTRIC | NEMA 12 | ROCKY MOUNTAIN | 92487 | 2017-05-23 | 2017-11-28 | 400 | [8 empty] | 10/24 | NO FAT REQUIRED |  |  | 2017-07-22 |  | 2017-08-04
51418-1 | STORE # 231 WESLACO | LV ATS SWGR | ERE | 54076 | 7/18 | 11/10 11/17 12/1 | 124 | 11/2 REV 11/13 |  | DONE
51511-1 | SUNNYVALE | ADD CAM LOCKS | AUTONOMY TECHNOLOGY | 995 | 11-6-17 | 2017-12-07
51400-3 | MACY'S BLDG | PANELS | WALTERS WHOLESALE | 2082 | 6/29 | 2017-12-06 | 100 | [9 empty] | NEED TO REVISE PANELS CUSTOMER WILL CALL CANS |  |  | 11/6
51516-1 -2 -3 -4 -5 -6 | WILDOMAR BLDG 6 | 1200A SWBD PANEL PANEL PANEL PANEL PANEL | WALTERS WHOLESALE | 40058 | 2017-11-20 |  | 123.4 | [9 empty] | SUBMITTALS DUE 4-6 WEEKS CUSTOMER CANCELLED THIS JOB 12/7 |  |  | 12/15
51126-1 | AAFB FIRE STATION | 800A DIST N4X | GEXPRO | 11876 | 8/2/16 | 11/13 11/20 11/27 | 48 | 2017-10-10 | 10/10 | 10/17 10/23 | 10/18 | 10/25 | 10/26 | 11/3 | 11/6 |  |  |  |  | 10-26-16 DONE |  | 2017-10-09
51487-1 | EASTVALE | SWBD 800A 65kAIC | WALTERS WHOLESALE | 5779 | 9/20 | 11/29 12/6 | 30 | 10/20 |  | 11/3 | 11/6 | 11/13 | 11/14 | 11/22 | 11/27 |  |  |  |  | 9/27 DONE |  | 10/18
51491-1 | STORE # 741 MONT BELVIEU | LV ATS SWGR | ERE | 61707 | 9/27 | 11/24 11/28 12/8 12/12 | 127 | 2017-11-17 |  | DONE | [6 empty] | LS50
51447-1 | STORE # 738 RICE & BISSONNET | LV ATS SWGR | ERE | 62304 | 8/16 | 11/10 11/17 11/24 12/1 12/8 12/12 | 127 | 2017-11-15 |  | DONE | [6 empty] | MISSING EP101ULC01
51448-1 | GOSLING ROAD HEB 2920 | LV ATS SWGR | ERE | 61707 | 8/16 | 11/17 11/24 12/1 12/8 12/12 | 127 | 2017-11-13 |  | DONE | [6 empty] | MISSING EP101ULC01
51420-1 | STORE #291 HARLIGTEN 02 | LV ATS SWGR | ERE | 59827 | 7/18 | 11/17 11/24 12/1 12/8 | 127 | 2017-12-05 |  | DONE | [6 empty] | MISSING EP101ULC01
51307-1 | NIM PROJECT BL | NEMA 1 4000A 400/230V 3P-4W | BL HARBERT | 18813 | 1/16 | 10/31 11/15 11/30 12/15 | 250 |  |  | DONE | [5 empty] | 10/24 10/25 | INVOICE 95% |  |  |  | 2017-02-10 | 2017-04-12
51307-2 | NIM PROJECT BL | LV SWITCHGEAR TYPE 1 INDOOR 5000A | BL HARBERT | 11226 | 1/23 | 10/31 11/15 11/30 12/15 | 250 |  |  | MZ | [5 empty] | 10/24 10/25 | INVOICE 95% |  |  |  | 2017-02-10 | 2017-04-12
51307-3 | NIM PROJECT BL | LV SWITCHGEAR TYPE 1 INDOOR 5000A | BL HARBERT | 11280 | 1/23 | 10/31 11/15 11/30 12/15 | 250 |  |  | MZ | [5 empty] | 10/24 10/25 | INVOICE 95% |  |  |  | 2017-02-10 | 2017-04-12
51307-4 | NIM PROJECT BL | CONTROL PANEL | BL HARBERT |  | 1/16 | 10/31 11/15 11/30 12/15 | 250 |  | 5/19 DONE | 5/22 | 6/9 | 6/12 | 6/30 | 7/5 |  | 10/24 10/25 | INVOICE 95% |  |  | 2017-02-10 | 2017-04-12 | 2017-04-28
51384-1 | BP ANACORTES | IPC | BP | 408602 | 6/12 | 12/1 12/18 | 1588 | [7 empty] | 11/17 | 12/12 | CUSTOMER WILL BE HERE FROM 12/12 thru 12/ 13 |  | WEE | 2017-07-21 |  | 2017-10-11
51352-1 -2 | NCS HOMEPORT | METAL ENCLOSED N4X SW 4000A | FLUID TECHNOLOGY | 292680 | 4/4/17 | 11/30 12/18 12/20 | 450 | 2017-08-21 |  | TA 9/1 9/11 9/29 | [5 empty] | 12/18 | NEED 3 WEEKS ADVANCE NOTICE FOR CUSTOMER GOVERNMENT FAT !!! |  | 9/11 | 2017-05-09 | 5/12 6/23 DONE | 2017-08-18
51452-1 | STORE # 92 VICTORIA | LV ATS SWGR | ERE | 68328 | 8-21 | 11/24 11/28 12/8 12/15 12/27 | 130 | 2017-12-04 |  | DONE | [11 empty] | 2017-11-29
51453-1 | STORE # 223 ALICE | LV ATS SWGR | ERE | 60937 | 8-21 | 11/24 11/28 12/8 12/15 12/27 | 127 | 2017-12-04 |  | DONE
51074-3 4 | P776 CORONADO | USB 1600 N1 USB 800A N1 | WALTERS WHOLESALE | 71329 | 6/27/16 | 12/18 12/20 | 587 | 2017-11-06 |  | MZ 11/20 DONE | [6 empty] | RELEASED -3 & -4 ON 11-3-17 |  |  | 11/2 DONE
51454-1 | STORE #401 KINGSVILLE | LV ATS SWGR | ERE | 54076 | 8-21 | 11/24 12/8 12/15 12/20 1/2 | 124 | 2017-11-20 |  | DONE
51456-1 | HEB STORE 554 | ATS 2500-2500 | ERE | 59827 | 8-21 | 12/1 12/15 12/21 1/2 | 127 |  |  | DONE | [11 empty] | 2017-11-29
51455-1 | HEB STORE 449 | ATS 2500-2000 | ERE | 59827 | 8-21 | 12/1 12/8 12/15 12/20 1/5 | 127 | 2017-12-04 |  | DONE
51457-1 | HEB STORE 488 | ATS 2000-2000 | ERE | 54076 | 8-21 | 12/1 12/15 12/21 1/5 | 127 | 2017-11-29 |  | DONE | [11 empty] | 2017-11-29
51517-1 | HARLEY KNOX B | 1200 DIST SECTION | AMERICAN ELECTRIC | 8517.6 | 2017-11-27 | 2017-01-08 |  | 12/7 |  | DONE | [6 empty] | DONE SCHEDULE TO SHIP 1/8
51458-1 | HEB STORE 95 | ATS 3200-3000 | ERE | 68328 | 8-21 | 12/8 12/15 12/21 1/5 1/12 | 127 | 12/4 |  | DONE | [11 empty] | 12/4
51459-1 | HEB STORE 236 | ATS 2000-2000 | ERE | 54076 | 8-21 | 12/8 12/22 1/5 1/12 | 127 | 12/4 |  | DONE | [11 empty] | 12/3
51460-1 | HEB STORE 373 | ATS 2500-2000 | ERE | 59827 | 8-21 | 12/8 12/22 1/12 | 127 | 12/4 |  | DONE | [11 empty] | 12/3
51540-1 | BURGER KING | 800A SWBD 2 SECTIONS | BORDER STATES ELECTRIC | 13920 | 2018-01-05 | 2018-01-16 |  | 2018-01-08 | [8 empty] | *****PREMIUM ****** MUST SHIP 1/16 GOING TO ARIZONA
51085-32 | HEB STORE 675 | ATS 3000-2500-SS1 | ERE | 63334 | 11-2 | 12/22 1/5 1/19 | 150 | 11/13 12/28 | [8 empty] | 3 SECTIONS **MUST SHIP ON 1/19**** |  | 2018-12-28 | 2018-11-09 |  | 2018-12-19
51107-1 | HART KAM HWY | GROUND BUS ASSEMBLY | FLUID TECHNOLOGY | 900 | 2016-07-21 | 2017-01-23 |  | 12/28 |  | MZ 12/28 | [11 empty] | 12/26
51359-1 | MAUI HEAVY INDUST | MCC SWITCHBOARD | FLUID TECHNOLOGY | 47110 | 4/21/17 | 12/22 1/23 | 239 | 2017-07-18 |  | DONE | [5 empty] | 2018-01-17 | MCC ARRIVED 12/1 |  | 9/10 | 5/12 5/22 DONE
51360-1 | EVANS HOLDING WATER | MCC SWITCHBOARD | FLUID TECHNOLOGY | 47110 | 4-21-17 | 12/22 1/23 | 120 | 2017-08-08 |  | DONE | [5 empty] | 2018-01-17 | MCC ARRIVED 12/1 |  |  | 5/12 5/22 DONE |  | 2017-08-07
51321-1 -2 -3 | SA ATLANTA FACILITY | SWITCHGEAR DOORS | SA RECYCLING | 12796 | 2/6 | 2017-01-24 | 40 | 2017-12-28 |  | MG DONE |  |  | 2018-01-10 |  |  | 2018-01-22 | CUSTOMER WILL BE HERE @7AM ON 1/23 |  | YES | 2017-04-19 |  | 2017-12-18
51461-1 | HEB STORE 479 | ATS 2500-2000 | ERE | 59827 | 8-21 | 12/15 12/22 1/19 1/26 | 127 | 2017-12-04 |  | DONE | [8 empty] | 2018-12-04 | 2018-11-30 |  | 2018-12-04
51462-1 | HEB STORE 586 | ATS 2500-2500 | ERE | 59827 | 8-21 | 12/15 12/22 1/19 | 127 | 2017-11-29 |  | DONE | [8 empty] | 2018-11-29 | 2018-11-28 |  | 2018-12-03
51483-1 | HEB STORE 734 | ATS 2500-2500 | ERE | 62304 | 2017-09-08 | 2017-01-26 | 127 | 2018-12-20 |  | DONE 11/30 | [6 empty] | *****MUST SHIP 1/26***** |  | 2018-12-20 | 2018-12-20 |  | 2018-12-15
51463-1 | HEB STORE 591 | ATS 3200-3000 | ERE | 68328 | 8-21 | 12/15 12/22 1/26 | 127 | 2017-12-04 |  | DONE | [8 empty] | 2018-12-04 | 2018-12-04 |  | 2017-12-04
51465-1 | HEB STORE 381 | ATS 2500-2500 | ERE | 59827 | 8-21 | 12/22 1/5 1/26 | 127 | 2017-12-11 |  | DONE 11/9 | [8 empty] | 2018-12-11 | 2018-12-05 |  | 2018-12-15
51499-1 | POTENTIAL INDUSTRIES | CT & Dist 2-Sec | MY ELECTRICAL SUPPLY | 14375 | 2017-10-09 | 1/24 1/29 1/31 |  | 12/18 |  | AM 1/2 | [6 empty] | WL BREAKER IS DUE TO SHIP 1/17 SHIP DATE CHANGED CUSTOMER HAS BEEN NOTIFED |  |  | DONE |  | 12-15
51486-1 | HEB STORE 642 | ATS 3000-2500 | ERE | 60937 | 2017-09-18 | 2017-02-02 | 127 | 2017-12-28 |  | DUE 1/10 | [6 empty] | *****MUST SHIP 2/2***** |  | 2018-12-28 | 2018-12-20 |  | 2017-12-21
51445-1 | LA FAMILA | PANEL | GRAYBAR ELECTRIC | 1740 | 8/14 |  | 3 | [9 empty] | CUSTOMER WILL CALL THE CAN CUSTOMER CANCELLED THE ORDER |  |  | 2017-08-16
51481-1 | HEB STORE 13 | ATS 3000-2500 | ERE | 60344 | 9-18 | 12/30 1/12 2/2 | 127 | 2018-12-20 |  | DONE 11/28 | [8 empty] | 2018-12-20 | 2018-12-13 |  | 2018-12-15
51464-1 | HEB STORE 495 | ATS 2500-2000 | ERE | 59827 | 8-21 | 12/22 1/5 2/2 | 127 | 2017-12-11 |  | DONE | [6 empty] | DONE |  | 2018-12-11 | 2018-12-05 |  | 2018-12-11
1255-2 | VEOLIA WATER PALM SPRINGS | IPC CONTROL ROOM | VEOLIA WATER | 83828 | 2/4/2017 | 1/23 2/5 | 486 |  |  | MG 12/20 DONE |  |  | 2018-01-26 |  |  | 2018-02-02 | Needs RADCO approval |  | YES | 5/5/2017 DONE
51485-1 | HEB STORE 562 | ATS 2000-2000 | ERE | 55186 | 2017-09-18 | 2018-02-16 | 127 | 2017-12-29 |  | AM 11/08 DONE | [8 empty] | 2018-12-29 | 2018-12-19 |  | 2017-12-21
51543-1 | NEGNOLIA PROJECT | 15" MTR DOORS | AMERICAN ELECTRIC | 630 | 2018-01-15 | 2018-01-31 | 2 | 1/18 |  | MZ DONE | [6 empty] | .
51482-1 | HEB STORE 381 | ATS 2500-2500 | ERE | 59827 | 9-18 | 12/30 1/12 2/9 | 127 | 2018-12-20 |  | AM 11/29 | [8 empty] | 2018-12-20 | 2018-12-14 |  | 2018-12-18
51484-1 | HEB STORE 431 | ATS 2000-2000 | ERE | 62304 | 2017-09-08 | 2017-02-09 | 127 | 2017-12-28 |  | DONE 12/4 | [8 empty] | 2018-12-28 | 2018-12-19 |  | 2017-12-20
51492-1 | HEB STORE 737 | ATS 3000-2500 | ERE | 62304 | 9/27 | 12/22 1/12 1/26 2/16 | 127 | 2017-12-29 |  | AM 1/11 DONE | [8 empty] | 2018-12-29 | 2018-12-20 |  | 2017-12-20
51531-1 | AAA PANELBOARD | PANEL | AAA ELECTRIC CUPPLY | 900 | 2017-12-28 | 2018-02-14 | N/A | 1/3 |  | N/A | N/A | N/A | N/A | N/A |  |  | PANEL WAS PURCHASED SCHEDULE TO SHIP 1/30
51217A-1 -2 | ELLSWORTH | BUS SUPPORT AND BOX FIELD SERVICE | EAFB |  |  | 1/12 1/31 2/6 |  |  |  | MG 1/29 DONE | [6 empty] | NEED TO SHIP THIS MONTH SCHEDULE FIELD SERVICE 1-29-18 CUSTOMER IS REQUESTING 6 CT'S
51544-1 -2 -3 -4 -5 -6 | PRATER MEDICAL EXPANSION | PANEL PANEL | REXEL | 11801 | 2018-01-17 | 2018-02-13 | 12 |  |  | SC 1/22
51231-1 -2 -3 | SASBO ELEMENTRY | 800A SWBD PANELBOARD 1600A SBRD | GEXPRO | 57547.38 | 2016-10-11 | 1/30 2/5 2/9 2/14 | 120 | 2017-12-04 |  | LF/MZ 1/8 1/15 | [6 empty] | CUSTOMER WANTS 51231 AND 51509 TO SHIP TOGETHER. SHIP DATE MIGHT CHANGED CUSTOMER HAS BEEN NOTIFED |  |  | 3/22 DONE | 2017-05-03
51509-1 -2 -3 -4 -5 -6 | SASEBO ELEMENTARY | NEMA 4X PANEL NEMA 4X PANEL ENCLOSED CB ENCLOSED CB ENCLOSED CB ENCLOSED CB | GEXPRO | 6122 | 11/2 | 1/30 2/5 2/9 2/14 | 16 | 11/30 |  | MZ DONE | [6 empty] | THE PANELS ARE BUYOUTS N4X WILL BE FABRICATED BY PCEP HANDLES ORDERED ON JS10700 4X BOXES WILL BE COMPLETED ON 1/12 (NEED TO BE PAINTED) |  |  | 11/2 DONE |  | 11/27
JS10700-1 | SASEBO ELEMENTARY | ENCLOSED CB | GEXPRO | 9203 | 2017-11-06 | 1/30 2/5 2/14 |  | 12/4 | [13 empty] | 11/27
51515-1 | SERVCO HRDROGEN FUELING | NEMA 3R SS WRAP 2 SECTIONS SS | FLUID TECHNOLOGY | 8790 | 11/10 | 2018-02-15 | 59 | 12/11 |  | 1/31 | [6 empty] | SWITCHBOARD IS SCHEDULE TO ARRIVE 1/26 SHIPDATE IS 3-4 WEEKS AFTER SWITCHBOARD ARRIVES |  |  | 11/15 DONE |  | 12/8
51502-1 | HEB STORE 225 | ATS 2500-2500 | ERE | 60937 | 10/11 | 1/26 2/16 | 127 | 2018-01-22 |  | AM DONE | [8 empty] | 2018-01-22 | 2018-01-15 |  | 2018-01-21
51518-1 | HEB STORE 581 | ATS 2500-2500 | ERE | 59827 | 2017-11-28 | 2018-02-16 | 127 | 1/8 |  | AM DONE | [9 empty] | 1/3 |  | 1/7
51085-44 | HEB STORE 473 | ATS 2500-2500 | ERE | 56494 | 3-17 | 11/17 11/24 12/15 2/16 | 127 | 2018-01-09 |  | AM DONE | [9 empty] | 2018-11-15 | 2018-01-08 | 2018-01-08
51546-1 | MCALLEN ENCLOSED BREAKERS | ENCLOSED BREAKERS (DROP SHIP) | ERE | 9170 | 2018-01-22 | 2018-02-28 | N/A
51512-1 | HEB STORE 747 | ATS 2000-2000 | ERE | 54846 | 2017-11-07 | 2018-02-26 | 124 | 2018-12-20 |  | DONE 11/28 | [8 empty] | 2018-12-20 | 2018-12-14 |  | 2018-12-18
51532-1 | HEB STORE 553 | ATS 2000-2000 | ERE | 59827 | 2018-12-28 | 2018-02-26 | 124 | 1/8 |  | DUE 1/25 | [11 empty] | 1/7
51524-1 | HEB STORE 672 | ATS 2500-2500 | ERE | 59827 | 2018-12-07 | 2018-02-26 | 127 | 1/12 |  | AM DONE LF 2/2 | [8 empty] | 2018-01-12 | 1/5 |  | 1/8
51525-1 | HEB STORE 668 | ATS 2500-2500 | ERE | 59827 | 2018-12-07 | 2018-02-26 | 127 | 1/12 |  | AM DONE | [8 empty] | 2018-01-12 | 1/5 |  | 1/8
1255-1 | VEOLIA WATER PALM SPRINGS | IPC-ELECTRICAL ROOM | VEOLIA WATER | 492071 | 2/4/2017 | 2018-02-27 | 1310 | 2018-10-19 |  | MG DONE |  |  |  |  | 2-12 | 2018-02-21 | Needs RADCO approval |  |  | 5/5/2017 DONE
51542-1 -2 | HC 5500 JEFFERSON | (2) PANELS | CAPITAL WHOLESALE | 6229 | 2018-01-15 | 2018-02-19 | 2 | 2018-01-18 | [8 empty] | IT WILL REQUIERE SOME ASSY PANEL IS SHIPPING FROM TX
51085-23 | HEB STORE 709 | ATS 3000-2500 | ERE | 60942 | 2018-12-28 | 2018-03-02 | 127 | 1/15 |  | AM DONE LF 2/5 | [8 empty] | 2018-01-15 | 1/8 |  | 1/15
51085-33 | HEB STORE 667 | ATS 2000-2000 | ERE | 56803 | 2018-12-28 | 2018-03-02 | 124 | 1/15 |  | AM DONE LF 2/6 | [8 empty] | 2018-01-15 | 1/9 |  | 1/14
51085-36 | HEB STORE 54 | ATS 2500-2500 | ERE | 59827 | 2018-12-28 | 2018-03-09 | 127 | 1/15 |  | AM 2/2 LF 2/7 | [8 empty] | 2018-01-15 | 1/9 |  | 1/14
51085-46 | HEB STORE 646 | ATS 2000-2000 | ERE | 54076 | 2018-12-28 | 2018-03-09 | 124 | 1/15 |  | AM 2/8 LF 2/13 | [8 empty] | 2018-01-15 | 1/10 |  | 1/14
51085-47 | HEB STORE 574 | ATS 2000-2000 | ERE | 56803 | 2018-12-28 | 2018-03-09 | 127 | 1/15 |  | AM 2/12 LF 2/14 | [8 empty] | 2018-01-15 | 1/10 |  | 1/15
51085-37 | HEB STORE 491 | ATS 3000-3000 | ERE | 64507 | 2018-12-28 | 2018-03-16 | 130 | 1/22 |  | LF/AM 2/13 DONE | [7 empty] | 1/17 | 2018-01-22 | 1/17 |  | 1/21
51534-1 | HEB STORE 563 | ATS 2500-2500 | ERE | 64750 | 2018-01-02 | 2018-03-16 | 127 | 2018-01-30 |  | AM DONE 2/6 | [7 empty] | 2018-01-17 | 2018-01-30 | 2018-01-17 |  | 2018-01-21
RA51085-2 | HEB STORE 63 | ERE-HEAT -KIT | ERE |  |  | 2018-03-20
RA51085-5 | HEB STORE 292 | ERE-HEAT -KIT | ERE |  |  | 2018-03-23
RA51085-16 | HEB STORE 627 | ERE-HEAT -KIT | ERE |  |  | 2018-03-20
RA51290-1 | PEPPERL FUCH | ERE-HEAT -KIT | ERE |  |  | 2018-03-29
51085-38 | HEB STORE 599 | ATS 2500-2500 | ERE | 60937 | 2018-12-28 | 2018-03-23 | 1900-05-06 | 2018-01-22 |  | AM/LF DONE | [7 empty] | 2018-01-16 | 2018-01-22 | 2018-01-16 |  | 2018-01-21
51533-1 | HEB STORE 423 | ATS 3000-2000 | ERE | 58039 | 2018-01-02 | 2018-03-23 | 1900-05-03 | 2018-01-22 |  | AM/LF DONE | [7 empty] | 2018-01-15 | 2018-01-22 | 2018-01-15 |  | 2018-01-21
51536-1 | HEB STORE 747 | ATS 2000-2000 | ERE | 54076 | 2018-01-03 | 2018-03-23 | 1900-05-03 | 2018-02-05 |  | AM/LF 3/5 DONE
51550-1 -2 -3 -4 | RV RESOURCE | PANELS | ONE SOURCE | 7364 | 2018-02-01 | 2018-03-27 |  | 2/27 |  | N/A |  |  |  | 2018-03-20 | 2018-03-21 |  | WILL CALL 3/27 |  |  |  |  | 2/23
51074-1 -2 | P776 CORONADO | 1600A N3R SS 800A N3R SS | WALTERS WHOLESALE | 71329 | 6/27/16 | 3/19 3/27 | 1901-08-09 | 2018-01-15 |  | MZ 2/16 |  |  | 2/16 3/23 |  | 2018-03-23 |  |  | 2018-08-22 |  | 2016-08-22 | 2018-01-03 | 2018-01-10
RA51085-6 | HEB STORE 497 | ERE-HEAT -KIT | ERE |  |  | 2018-03-28 | [10 empty] | SHIPPED 3-29
RA51085-9 | HEB STORE 687 | ERE-HEAT -KIT | ERE |  |  | 2018-03-28 | [10 empty] | SHIPPED 3-29
RA51085-7 | HEB STORE 541 | ERE-HEAT -KIT | ERE |  |  | 2018-03-28 | [10 empty] | SHIPPED 3-29
RA51085-24 | HEB STORE 575 | ERE-HEAT -KIT | ERE |  |  | 2018-03-28 | [10 empty] | SHIPPED 3-29
51471-1 | REPLACE SUBSTATION F8B | CIRCUIT BREAKER CONTROL (TYPICAL FOR 2) | FLUID TECHNOLOGY | 11150 | 9/8 | 2018-03-29 | 1900-02-08 | 2018-01-10 |  | MZ/LF 1/15 DONE |  |  | 2018-03-16 | 2018-03-22 | 2018-04-03 |  | shipped 4-4-18 | 9/29 DONE |  | 9/29 DONE |  | 2018-01-03
51556-1 | WEST COAST TURF | (-1)SES 3R DIST 1200A (-2)500 HP SS OPEN STYLE INSTALLED BLANK | ELITE ELECTRICAL SUPPLY | 18145 | 2018-02-15 | 3/29 4/5 |  | 2018-03-06 | 2018-04-04 | AM/LF 3/8 | 2018-03-12 | 2018-03-18 | 2018-03-19 | 2018-03-26 | 3/27 4/5 |  | shipped 4-4-18 | 2018-03-02 | 2018-03-06 | 2018-03-02 | N/A | 2018-03-02
51567-1 | HABOR CITY REC CENTER | EMPTY ENCLOSURE | ELECTRO CONSTRUCTION | 3271.86 | 2018-03-21 | 2018-03-28 |  | 2018-03-21 |  | 2018-03-22 | 2018-03-23 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-28 |  | shipped 4-4-18
51535-1 | HEB 552 | ATS 3000-2500 | ERE | 60344 | 2018-01-03 | 2018-03-28 | 1900-05-06 | 2018-02-05 |  | AM/LF 3/5 DONE | [6 empty] | shipped 4-6-18
51538-1 | ROYCE CITY BUCEE'S | ATS 2500-2500 | ERE | 59827 | 2018-01-04 | 2018-03-28 | 1900-05-06 | 2018-02-05 |  | AM/LF 3/5 DONE | [6 empty] | shipped 4-6-18
51537-1 | HKE SWBD | 2000A SWBRD | GEXPRO | 23985 | 2018-01-04 | 3/14 3/23 3/28 | 1900-04-15 | 2/6 |  | LF/AM 2/27 DONE | 3/6 | 3/13 | 2018-03-14 | 3/21 | 3/22 |  | shipped 4-6-18 | FA 1/31 DONE |  | FA 1/31 DONE | N/A | 2/6
51569-1 | Hoffy Dog | 600 panel TYPE 4X | Royal | 5550 | 2018-04-03 | 2018-04-06 |  |  | DONE mtrl I/S | 4/3 DONE | 2018-04-03 | 2018-04-05 | 2018-04-03 | 2018-04-06 | 2018-04-06 |  | PREMIUM shipped 4-6-18 | 2018-04-03
51386-1 -2 | DOW PITTSBURG | NEMA 3R SWGR NEMA 3R SWGR | INDEPENDENT ELECTRICAL | 35770 | 6/12 | 3/19 3/26 3/28 | 1900-05-29 | 1/23 |  | MZ 2/9 DONE | [6 empty] | DONE TRYING TO FIND CARRIER SHIPPED 4-13-18 | 9/9/17 DONE |  | 9/7/17 DONE
RA51295-1 | STORE #30 WHARTON BUC-EE'S | ERE-HEAT -KIT | ERE |  |  | 2018-04-06 | [10 empty] | SHIPPED 4-13
RA51295-2 | STORE #18 WALLER BUC-EE'S | ERE-HEAT -KIT | ERE |  |  | 2018-04-06 | [10 empty] | SHIPPED 4-13
RA51295-3 | STORE #33 TEXAS CITY BUC-EE'S | ERE-HEAT -KIT | ERE |  |  | 2018-04-06 | [10 empty] | SHIPPED 4-13
RA51295-4 | STORE # BAYTOWN BUC-EE'S | ERE-HEAT -KIT | ERE |  |  | 2018-04-06 | [10 empty] | SHIPPED 4-13
RA51295-7 | STORE #40 KATY BUC-EE'S | ERE-HEAT -KIT | ERE |  |  | 2018-04-06 | [10 empty] | SHIPPED 4-13
RA51328-1 | STORE# 3 BRAZORIA BUC-EE'S | ERE-HEAT -KIT | ERE |  |  | 2018-04-06 | [10 empty] | SHIPPED 4-13
RA51085-22 | HEB STORE 474 | ERE-HEAT -KIT | ERE #1 |  |  | 2018-04-13
RA51382-1 | 15440 UTILITY TRAILER | DIST SEC 800A | AMERICAN ELECTRIC |  | 2017-06-01 | 2018-04-17 |  | 2018-04-05 | IN STOCK | [7 empty] | LEFT OFF PREVIOUS ORDER - RUSH TO CUSTOMER; SHIPPED 4-18 | 2018-04-05 |  | 2018-04-05 |  | 2018-04-05
RA51085-39 | HEB STORE 645 | ERE-HEAT -KIT | ERE #4 |  |  | 2018-04-20 | [10 empty] | SHIPPED 4-20-18
RA51085-10 | HEB STORE 698 | ERE-HEAT -KIT | ERE #4 |  |  | 2018-04-20 | [10 empty] | SHIPPED 4-20-18
RA51085-4 | HEB STORE 99 | ERE-HEAT -KIT | ERE #4 |  |  | 2018-04-20 | [10 empty] | SHIPPED 4-20-18
RA51085-1 | HEB STORE 616 | ERE-HEAT -KIT | ERE #4 |  |  | 2018-04-20 | [10 empty] | SHIPPED 4-20-18
51392-1 -2 -3 | P66 SUB ST-1 | -1 IPC NON INSULATED -2 LV DIST SWBRD -3 BEMAG XFRM | ROYAL WHOLESALE | 200773 | 6-19 | 2/22 2/28 3/19 3/26 3/29 | 1902-04-13 | 11/26 |  | MZ 1/19 MG 1/19 DONE |  |  |  | 3/19 | 3/9- 3/13 | 2018-03-21 | SHIPPED 3-28, O&M's DUE BY 4/11 | 8/3 8/8 DONE |  | 8/3 8/8 DONE |  | 11/23
51308-1 -3 | KALIHI PUMP STATION | MCC PLUS C/O TERM CAB 4X | FLUID TECHNOLOGY | 220140 | 1/16/2017 | 2018-04-11 | 1902-05-24 | 2018-01-10 |  | MZ AM LF 3/7 |  |  | 2018-03-12 |  | 2018-04-02 | 2018-04-16 | SHIPPED 4-30-18 |  |  | 2-28-17 3-29-17 | 11/16 DONE | 2017-12-29
51527-1 | INDIAN SKIES | NEMA 3R NWA 4.16 ME SWGR 600A | CITY ELECTRIC SUPPLY | 39990 | 2017-12-08 | 2018-04-12 | 1900-07-17 | 2/22 |  | MZ/LF 3/12 | 3/9 3/12 | 3/23 | 2018-03-26 | 4/9 | 4/10 |  | SHIPPED 4-30-18 |  |  | FA 1/19 DONE |  | 2/15
51558-1 | TEXAS A&M | ATS CONTROL CABINET | ERE | 44750 | 2018-02-22 | 2018-04-20 |  | 2018-03-26 |  | 2018-04-02 | 2018-04-03 | 2018-04-10 | 2018-04-11 | 2018-04-18 | 2018-04-19 |  | SHIPPED 4-27-18 | 43174 | 2018-03-26 | 2018-03-23 |  | 3/15
RA51085-11 | HEB STORE 705 | ERE-HEAT -KIT | ERE #5 |  |  | 2018-04-27 | [10 empty] | SHIPPED 4-27-18
RA51233-1 | HEB STORE 731 | ERE-HEAT -KIT | ERE #5 |  |  | 2018-04-27 | [10 empty] | SHIPPED 4-27-`8
RA51200-1 | PLANET FORD | ERE-HEAT -KIT | ERE #5 |  |  | 2018-04-27 | [10 empty] | SHIPPED 4-27-18
RA51085-8 | HEB STORE 656 | ERE-HEAT -KIT | ERE #5 |  |  | 2018-04-27 | [10 empty] | SHIPPED 4-27-18
51565-1 51565-2 | IPPUDO | SPLIT-BUS PANELS | ADVANCE WHOLESALE | 6120 | 2018-03-13 | 2018-04-27 | [10 empty] | shipped 5-11-18 delivered Angelo | SC
51583-1 -2 | GOODMAN LOGISTIC CENTER | PANELS | WALTERS CERRITOS | 3864 | 2018-05-16 | 2018-05-18 |  | 2018-05-16 | [8 empty] | PREMIUM SHIPPED 5-18-18 | 5-16
51578-1 | NEW CASTLE CHINO HILLS; GREGG# 16960-2S-7A | 2000A UGPS | AMERICAN ELECTRIC | 2269.8 | 2018-05-03 | 2018-05-31 |  | 2018-05-08 |  |  | 5-11 | 5-21 | 2018-05-22 | 5-29 | 5-30 |  | DONE - SHIPPED 5-21-18 | 5-4 |  | RECORD ONLY
51571-1 | MACY'S | MTR-MAIN 400A | WALTERS WHOLESALE | 5623 | 2018-04-10 | 2018-06-04 |  | 2018-05-04 |  | 2018-04-02: 2018-05-07 |  | DONE - SHIPPED 5-21-18 | RS 4-12 |  | 4-13 |  | 5-1
51554-1 -2 -4 -3 | JAVIERS UTC | 800A SWBD PANEL PANEL PANEL | WALTERS WHOLESALE | 15218 | 2018-02-09 | 2018-05-08 |  |  |  | 2018-04-11: 43160; 2018-04-19: 2018-03-01 |  | SHIPPED 5-24-18
51451-1 -2 | CRIMISON PIPELINE (MONSTROSITY) | 400A SES PNL | ROYAL WHOLESALE | 24168 | 8/17 | 3/14 3/19 3/29 5/25 5/30 | 1900-02-04 | 2018-02-26 |  |  | 2018-04-18 | 5-9-18 C/O PO, shipped 5-30 | 9/19 |  | 9/19 DONE | 11/17 DONE | 1/9 | 1/10 |  | LF 1/25 2/16
51576-1 51576-2 | TI MAIN SUBSTATION DOOR REPLACEMENT | SECTION 1A DOOR SECTION 2A DOOR | SA RECYCLING | 2550 | 2018-04-18 | 2018-07-26 |  |  |  | 2018-04-10: SITE VISIT MZ 5-7 DONE; subs due 6-4; 6-8 wks build; 2018-04-11: MZ & JA 5-31; 2018-04-19: 5/29 DONE |  | dwgs submitted 5-25 | NOT | release 7-6?
51539-1 | HEB STORE BUC-EES MELISSA | ATS 2500-2500 | ERE | 59827 | 2018-01-04 | 2018-05-31 | 1900-05-06 |  |  | 2018-04-10: **SITE AUDIT*** May 30; Approved to Mark. SHIPPED 6-1-18; 2018-04-18: 2018-02-05 |  | SHIPPED 6-1-18 | 2018-02-05 |  | AM/LF 3/5 DONE
51586-1 -2 -3 | COMTECH T.I. | PANELS | WALTERS ANAHEIM | 3376 | 2018-05-17 | 2018-06-15 |  |  |  | 2018-04-11: 5-17 |  | shipped 6-7-18 | 2018-05-18 | 2018-06-01
51588-1 | GE PANELBRDS | PANEL | ELECTRICAL SALES | 921 | 2018-05-21 | 2018-06-15 |  |  |  | 2018-04-11: 5-21 |  | shipped 6-7-18 | 2018-05-21 | 2018-06-01
51589-1 | UPS CITRUS 18220-2S-7C | BLANK DIST SEC 4000A | AMERICAN ELECTRIC | 7597 | 2018-05-18 | 2018-06-26 |  |  |  | 2018-04-10: ON SITE BY 6-28; 2018-04-11: RS |  | shipped 6-7-18 | 2018-05-23 |  | 5/23
51585-1 -2 | JOHNS WHOLESALE | PANELS | JOHN'S WHOLESALE | 1871 | 2018-05-17 | 2018-06-08 |  |  |  | 2018-04-10: shipped 6-8-18; 2018-04-11: 5-17 |  | shipped 6-8-18 | 2018-05-17
51399-1 | CITY OF POWAY | NEMA 3R | ONE SOURCE | 6250 | 6/28 |  | 137 |  |  | 2018-04-10: DONE WAS $25000, CANCELLATION FEE INVOICED 4-12-18; 2018-04-11: 7/20 DONE 8/9; 2018-04-19: 7/20 DONE 8/9 |  | CANCELLATION FEE INVOICE 4-12-18 | CHECK THIS! | CANCELLED?
51554-6 | JAVIERS UTC | PANEL | WALTERS WHOLESALE | 2599 | 2018-02-09 | 2018-06-06 |  |  |  | 2018-04-10: remaining item on job; 2018-04-11: 43160; 2018-04-19: 2018-03-01 |  | shipped 6-13-18 | 5-24--18
51597-1 -2 | POLICE DEPT UPLAND | DIST SEC 600A PANEL 125A | WALTERS WHOLESALE | 6713 | 2018-06-07 | 2018-06-13 |  |  |  | 2018-04-10: PREMIUM must deliver morning of 6-13 |  | shipped 6-13-18 | 2018-06-08
51570-1 | CIRCLE K | SES 2SEC 3R | AES | 7739 | 2018-04-09 | 2018-06-11 |  |  |  | 2018-04-10: waiting for Siemens switches - customer asks us to ship complete; 2018-04-11: 43200; 2018-04-19: AG 4/10/2018 |  | shipped 6-14-18 | 2018-04-13 | 2018-07-03 | 2018-04-22
R5108522A | HEB 474 | ERE-HEAT -KIT | ERE #6 |  |  | 2018-06-06 | [10 empty] | side entrance required, SHIPPED 6-18-18
R510855A | HEB 292 | ERE-HEAT -KIT | ERE #6 |  |  | 2018-06-06 | [10 empty] | side entrance required: photo SHIPPED 6-18-18
R5108524A | HEB 575 | ERE-HEAT -KIT | ERE #6 |  |  | 2018-06-06 | [10 empty] | side entrance required: photo SHIPPED 6-18-18
51396-1 | PG & E/ SWINGLE JUNCTION METER | IPC | ENERGY COMM | 101385 | 6-26 | 2018-03-29 | 1901-08-12 23:02 | 2018-03-12 | 2018-03-26 | 2018-03-27 |  |  | MG AM 8/18 DONE | DONE | MG AM 8/18 DONE |  | CUST TO WILL CALL MID JUNE ; CHARGING STORAGE; shipped 6-15-18 | 2/1 |  | MG DONE | 2018-02-22 | 2018-03-09
51587-1 | PARK LUCERO MODIFCATION: FOOTPRINT | 2500A CT MTR-MAIN WITH DIST | INDEPENDENT PHOENIX | 33964.25 | 2018-05-17 | 2018-06-19 |  | 2018-05-22 | NEUT SEN 6/4 | 2018-05-30 | 2018-05-31 | 2018-06-07 | 2018-06-08 | 2018-06-18 | 2018-06-19 |  | NEEDS TO ARRIVE BY 6-21-18; cust provide neutral sensor; shipped 6-20-18 | RS
51596-1 | RANCHO MIRAGE | SES 600A OH,CT,MAIN, DIST | MAIN ELECTRIC | 10125 | 2018-06-06 | 2018-06-22 |  | 2018-06-08 | 2018-06-20 | [7 empty] | PREMIUM; shipped 6-20-18
R510856A | HEB STORE 497 | ERE-HEAT -KIT | ERE #7 |  |  | 2018-06-22 |  | 2018-06-19 | [8 empty] | side entrance required SHIPPED 6-22
R510859A | HEB STORE 687 | ERE-HEAT -KIT | ERE #7 |  |  | 2018-06-22 |  | 2018-06-19 | [8 empty] | side entrance required SHIPEDP 6-22
R5108521 | HEB STORE 686 | ERE-HEAT -KIT | ERE #7 |  |  | 2018-06-22 |  | 2018-06-19 | [8 empty] | side entrance required SHIPPED 6-22
51601-1 | 51537 COVERS | REPLACE CVRS | KVA ELECTRIC | 450 | 2018-06-15 | 2018-06-22 |  | 2018-06-19 | [8 empty] | SHIPPED 6-22
51605-1 | GAUCHO GRILL | PANEL AB643 | JOHNS WHSL | 1993 | 2018-06-21 | 2018-06-22 |  | 2018-06-21 | [8 empty] | SHIPPED 6-22
51599-1 | ESI PANEL | 225A PANEL | Electrical Sales | 916 | 2018-06-14 | 2018-07-13 | [10 empty] | SHIPPED 6-22
51594-1 | GARY DIHEL LKH FARMS | 600A SES UG /CT/ DIST | DYKMAN ELECTRICAL | 6995 | 2018-05-31 | 2018-06-27 |  | 2018-06-11 |  | 2018-05-30: yes |  | PREMIUM SHIPPED 6-22
51612-1 -2 | VONS | SES 2000A 1200A DIST | INDUSTRIAL SUPPPLY | 54268 | 2018-06-28 | 2018-07-06 | [10 empty] | SHIPPED SES 6-30, JOB SHIPPED 7-5-18
R5108526 | HEB STORE 551 | ERE-HEAT -KIT | ERE #8 |  |  | 2018-07-11 | [10 empty] | SHIPPED 7-11
R5108510 | HEB STORE 698 | ERE-HEAT -KIT | ERE #8 |  |  | 2018-07-11 | [10 empty] | SHIPPED 7-11
51615-1 | MARKETING | DEMO RACK | PCEP |  |  | 2018-07-10 | [10 empty] | COMPLETED 7-11
51559-1 | 17300 AMAZON LGB8 | 12KV UGPS ON RIGHT CONTROL SECTION | AMERICAN ELECTRIC | 114552 | 2018-02-27 | 6-26 7-11-18 |  | 2018-05-29 | mersen fuses | 6-1 | 6-4 | 6-15 | 2018-06-18 | 6-22 | 6-25 | SCE 7-5 9:30AM | 51559 MUST DELIVER TUES 7-10 SHIPPED 7-10 |  |  | AG 3/14 DONE |  | 5-21-18
51607-1 -2 | GAUCHOO GRILL | PANELS 225A | JOHNS WHSL | 1699 | 2018-06-22 | 2018-07-13 |  | 2018-06-29 | done | [7 empty] | Cans picked up on 6-22; CUST REQUEST 7-10; SHIPPED 7-11-18
51040-1 | SHOPRITE BAYSHORE 2016 | GENERATOR SWITCHBOARD | UNISON | 54970 | 6/9/16 | 2018-07-16 | 177 | 2018-05-04 | name plates | [7 empty] | question on bus ampacity 2000A; full release from cust 5-8-18; asked for 6 wk expedite; SEL relay programing; SHIPPED 7-13-18 | 6/29 |  | 2016-06-29 | 6/15 6-23 1/29 | 43224
51504-1 | SHOPRITE SELDEN 2017 | TYPE 3R NON WALK- IN 1 GENERATOR SWB 200A | UNISON | 52015 | 2017-10-18 | 2018-07-20 | 201 | 2018-05-14 | cards 7-10 | [7 empty] | asked for 6 wk BUT expedite not approved; NEED SEL CARDS; SHIPPED 7-13-18 | 11/10 11/15 |  | 11/10 11/15 DONE | 1/31 | 5-9
51606-1 | Gary Dihel Farm | 800A SES W DIST | DYKMAN ELECTRICAL | 8840 | 2018-06-22 | 2018-07-20 |  | 2018-06-26 | [8 empty] | PREMIUM 4 WK EXPEDITE SHIPPED 7-11-18
51545-1 | TRADITIONS SENIOR HOUSING | (2)4000 (1) 2500A 5 SEC 46-4 CONDUITS | ERE | 166450 | 2018-01-18 | 2018-06-08 | [10 empty] | released to Production - purchasing issues threaten ship date; Interteck inspection 5-30; SHIPPED 7-12-18 | 3/18 |  | ET 2/9 | ET 3/18 DONE | 4-4
51576-1 51576-2 | TI MAIN SUBSTATION DOOR REPLACEMENT | SECTION 1A DOOR SECTION 2A DOOR | SA RECYCLING | 29031.7 | 2018-04-18 | 2018-07-19 |  | 2018-05-31 | due 6-26 | 2018-05-30: mz; 2018-06-19: 7-11 | 2018-07-17 | shipped 7-19-18 | MZ & JA 5-31 |  | 5/29 DONE |  | 5-31-18
51620-1 | Manhattan Bch Studios | 225A Panel | AAA ELECTRICAL | 1596 | 2018-07-16 | 2018-07-23 |  | 2018-07-15 | [8 empty] | PREMIUM will called 7-20; nameplates mailed 7-23
51621-1 | Manhattan Bch Studios | 225A Panel | AAA ELECTRICAL | 1596 | 2018-07-16 | 2018-07-23 |  | 2018-07-15 | [8 empty] | PREMIUM will called 7-20
51623 FS-7 | UNISON BURLINGTON | SERVICE | UNISON | 1350 | 2018-07-17 | 2018-07-20 | 7 | NONE | [8 empty] | FERIDUN REMOTE-IN TO SITE FOR REVIEW OF SYSTEM OPERATION; 100% progress billing at PO; complete 7-24-18
51624-1 | PANEL | PANEL B44 | ANTHONY WHSL | 995 | 2018-07-19 | 2018-07-26 |  | 2018-07-20 | [8 empty] | shipped 7-25-18
51619-1 | VALLEY APARTMENTS | 600A SES | ROYAL VERNON | 8775 | 2018-07-13 | 2018-07-27 |  | 7-717-18 | [8 empty] | shipped 7-26-18 | RS |  | 2018-07-17
50842-2 -3 | GROUND PADS | GROUND BUS ASSEMBLY | FLUID TECHNOLOGY | 3705 | 2/23/16 | 7-31 | 40 | 2018-07-11 | done | [7 empty] | shipped 7-25-18 | 2/23 |  | 2/23 |  | 6-25
51590-1 | BLOCK 800 NERI | PANEL | WALTERS WESTMINSTER | 1576 | 2018-05-21 | 2018-07-31 |  | 2018-07-03 | GE | [7 empty] | shipped 7-25-18 | SAL |  | 2018-05-22 |  | 7/3
51611-1 THROUGH -6 | SPACES HOLLYWOOD | (6) PANELS AB49B | CED-POWER ANAHEIM | 5125 | 2018-06-28 | 2018-07-27 |  | 2018-06-28 | GE cans & trim | [7 empty] | ship 7-27-18 | sal
51472-1 | UWALU WWPS | NEMA 4X TYPE 316 SS GENERATOR CABINET | FLUID TECHNOLOGY | 2450 | 9/11 | 7/20/2018 8-31-18 7-31-18 | 8 | 6/26/2018 7-19-18 | 2018-08-27 | [7 empty] | RELEASED 6-19-18 7-13-18 notified Fluid of revised ship date SHIPPED 7-30-18 | 9/13 |  | 9/13 DONE |  | 6-26-18
51610-1 | SAMPLE LISW | LISW | PCEP SAMPLE |  | 2018-06-28 | 2018-07-13 | [10 empty] | PCEP DESIGN-BUILD; SHIPPED 7-30-18
51628-1 | PLANET FITNESS | 3R WRAP OF GE SWITCHBOARD | AMERICAN ACE | 8346 | 2018-07-27 | 2018-08-03 |  | 2018-07-30 | [8 empty] | PREMIUM; WILL CALL;SHIPPED 8-3-18
51627-1 | PANEL | PANEL 18CKT 100A | WALTERS - BREA | 560 | 2018-07-25 | 2018-08-03 |  | 2018-08-02 |  | 2018-06-19: 8-3-18 |  | WILL CALL; SHIPPED 8-3-18
51602-1 | 17900 IDI LIVE OAK | 2000A SES & DIST | AMERICAN ELECTRIC | 15846.3 | 2018-06-18 | 2018-07-27 |  | 2018-06-26 | pwr supply! | 2018-05-30: 7-5 am; 2018-05-31: 2018-07-09 |  | Gregg 17900-2S-7A, FONTANA; 4 week ship; shipped 8-7-18 | u
51359A-1 | MAUI HEAVY change order | HIGH DISCHARGE PRESSURE SWITCH | FLUIDTECH | 1920 | 2018-07-19 | 2018-08-06 | 1900-01-04 | 2018-07-30 | [8 empty] | NEED TO ADD TO "AS BUILT" FOR 51359 AND PROVIDE MARK UP OF WIRING DIAGRAMS ON HOW TO INSTALL; shipped 8-6-18
51631-1 | PANEL COVERS | SHEET METAL - 2 COVERS | DANCO | 344 | 2018-08-01 | 2018-08-08 |  |  |  | 2018-05-30: refused to make drawing; 2018-06-07: done? |  | WILL CALL - RUSH JOB SHIPPED 8-8-18
51642-1 | VANTAGE LACC | PANEL | WALTERS | 1540 | 2018-08-14 | 2018-08-15 |  | 2018-08-14 | NONE | [7 empty] | WILL CALL shipped 8-15
51633-1 -2 | PETERSEN AUTO MUSEUM | PANEL 400A 480V PANEL 225A 480V | WALTERS | 3088 | 2018-08-03 | 2018-08-17 |  | 2018-08-03 | due 8-13 | [7 empty] | PREMIUM; WILL CALL; took cans on 8-3-18;; shipped 8-15
R5108529 | HEB STORE 724 | ERE-HEAT -KIT | ERE #9 |  |  | 2018-08-17 | [10 empty] | SHIPPED 8-17-18
51639-1 -2 | CHIPTON ROSS | PANEL 250A 208V PANEL 125A 208V | WALTERS | 1627 | 2018-08-10 | 2018-08-17 |  | 2018-08-14 | [8 empty] | WILL CALLED 8-2--18
51638-1 | CUSTOM ELECTRIC | PANEL 250A 208V 54 CKT | WALTERS | 809 | 2018-08-10 | 2018-08-17 |  | 2018-08-15 | [8 empty] | WILL CALLED 8-20-18
51614 | BLH#2 CVRS | CVRS for 51307 BLH | BLH | 10105 | 2018-07-02 | 2018-08-10 |  | 2018-07-09 | 7-20 | 2018-05-30: DONE |  | SHIPPED 8-22-18
51514-1 -2 -3 | DROUGHT RELIEF | (1) 800A DIST SWBD N3R (4) 600A DIST SWBD N3R | ROYAL INDUSTRIAL | 141925 | 11/10 | 2018-08-27 | 1902-01-05 | 5/8/2018; 6-6-18 | ge gfi bkrs | 2018-05-30: bases done |  | SHIPPED 8-21-18 | 12/15 DONE |  | 12/15 DONE | 1/30 | 6-7-18
51514A-1 51514B | DROUGHT RELIEF | (1) (600) DIST SWBD N3R | ROYAL INDUSTRIAL | 37210 | 2017-12-21 | 2018-08-27 | 1900-06-23 | 5/8/2018 6-6-18 | ge gfi bkrs | 2018-05-30: bases done |  | SHIPPED 8-21-18 | AG 1/16 |  | AG 1/16 DONE | 1/30 DONE | 6-7-18
51514D | DROUGHT RELIEF | ADD CB AND XFRM | ROYAL INDUSTRIAL | 18000 | 2018-08-06 | 2018-08-27 |  | N/A | N/A | 2018-05-30: N/A |  | SHIPPED 8-21-18
51632-1 | K&N REDLANDS | 4000A DIST SWBRD | MAIN-RIVERSIDE | 6830 | 2018-08-03 | 2018-08-28 |  | 2018-08-09 | 8-30 boltsw | 2018-05-30: AM 8-14 |  | SHIPPED 8-28-18 | RS |  | 2018-08-07
51519-2 | REGIMENTAL CONSOLIDATION FACILITY | ENCLOSURE NEMA 3R assy | FLUID TECHNOLOGY | 11725.02 | 2017-11-30 | 7/13/2018 8-15-18 | 20 | 2018-06-20 | 8-10 mtr-main & meter | [7 empty] | SHIPPED 8-31-18 | 12/8 |  | 12/8 DONE | 1/31 2/9 DONE | #2 =6-13-18
51604 -1 -2 -3 | OCEANFRONT & MOSS | 800A SES N4X 400A PNL N1 400A PNL N1 | WALTERS - RIVERSIDE | 18700 | 2018-06-21 | 2018-08-16 |  | 2018-07-12 | ge panel | [7 empty] | SHIPPED 8-31-18 |  |  | 6-29 RS SAL DONE |  | 8-16-18
51645-1 | ATLANTIC SQUARE | SES 1200A & Multi-Mtr (9) | Walters San Dimas | 19675 | 2018-08-17 | 2018-08-31 |  |  | should be stock | [7 empty] | SHIPPED 8-31-18 | RS |  | 8-20
51637-1 | HOME DEPOT REDLANDS | DIST SWBRD 2500A | AMERICAN ELECTRIC | 29837 | 2018-08-07 | 2018-09-05 |  | 2018-08-13 | sie v7 | [7 empty] | shipped 9-7-18 | RS | bar: 2018-05-30
51307D | BLH#2 | START-UP SERVICES | BLHI | 11000 | 2015-08-13 | 2018-09-01 |  | N/A | DONE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED, TECH HOME 9-1-18
51640-1 -2 | LIFE SAFETY BREAKERS | 100A 3P 480V 50A 3P 480V | ERE | 2596.5 | 2018-08-13 | 2018-09-04 |  |  | GE 9-4 | [7 empty] | SHIPPED 9-10-18 | RS
51656 | HOLD DOWN PLATES | ANCHOR PLATES | ROYAL BAKERSFIELD | 1200 | 2018-08-30 | 2018-09-14 | [10 empty] | SHIPPED 9-12-18 MADE FROM 3/4" 6" BAR
51652-1 | JAVIER'S UTC | 225A PANEL | WALTERS | 995 | 2018-08-28 | 2018-09-25 |  | 2018-08-30 | [8 empty] | SHIP ASAP - want ealy - back-order breakers - SHIPPED 9-13-18 | SAL
51641-1 | 17020 RIDGE | 4000A SES | AMERICAN ELECTRIC | 26567 | 2018-08-14 | 2018-09-14 | [10 empty] | ON SITE 9-14 RUSH! SHIPPED 9-14-18
51626-1 | PROLOGIS RIALTO 7, I-210 | SES 5 SEC 480V 4000A TYPE 1 | AMERICAN ELECTRIC | 20946 | 2018-07-26 | 2018-09-21 |  | 2018-08-03 | boltsw 8-20 | 2018-05-30: MZ PARTIAL 8-6; due 8-21 |  | GREGG # 16480-2S-7A 24HR NOTIFY; ready to ship early SHIPPED 9-14-18 |  |  | 2018-08-06
51662-1 | MENIFEE LAKES 1 | 400A SES MTR-MAIN - Type 3R | WALTERS- SAN DIMAS | 7036 | 2018-09-07 | 2018-09-17 |  | 2018-09-11 | [8 empty] | PREMIUM - IMMEDIATE RELEASE SHIPPED 9-17-18 | RS |  | 9-11-18
51593-1 | SNACK PLANT | ATS 4000-4000-B5 | ERE | 116905 | 2018-05-30 | 2018-09-14 |  | 2018-07-16 | ge 9-10? aux sw | 2018-05-30: AM done; 2018-06-19: 9-4 | 9-6 TEST | V3 WITH ICP UL891 DWGS 4-6, SHIP 8 WKS; SHIPPED 9-17-18 | et 6-22 |  | 6-28 DONE |  | 7-16-18
51107-2 -3 | HART KAM HWY | GROUND BUS ASSEMBLY | FLUID TECHNOLOGY | 2310 | 2016-07-21 | 2018-09-19 |  |  |  | 2018-05-30: MZ 8-13 |  | will ship Wednesday shipped 9-19-18
51634-1 | KEYSTONE | SES 1000A 480V OVERHEAD MTR-MAIN DIST | WALTERS | 11228 | 2018-08-03 | 2018-09-21 |  | 2018-08-15 | sie | 2018-05-30: NEED |  | WILL CALL RUSH!! - shipped 9-19-18 | RS
51630-1 -2 -3 | PROLOGIS EUCALYPTUS | SES 2000A SES 2000A SES 4000A | AMERICAN ELECTRIC | 39581 | 2018-07-27 | 2018-09-20 |  | 2018-08-08 | done | 2018-05-30: MZ 8-14? |  | GREGG 17500-2S-7B; notified of delay shipped 9-20-18 | RS
RA1255 1255A | VEOLIA PALM SPRINGS | START UP | VEOLIA NORTH AMERICA | 9151 | 2018-06-07 | 2018-08-02 |  |  | nameplates, handle | [7 empty] | FINAL ACCOUNTING 9-21-18
51675-1 | 18770 WAYFAIR | 1200A SES MTR-MAIN-DIST | AMERICAN ELECTRIC | 8567 | 2018-09-17 | 2018-10-11 | [10 empty] | CANCELLED 9-21-18
51673-1 | ARCO | 1000A SES 3R MTR-MAIN | REXEL TUALATIN OREGON | 1700 | 2018-09-19 | 2018-10-17 |  | 2018-09-21 | [8 empty] | DWGS 1 WEEK. HOLD FOR APPROVAL? SHIP 4 WEEKS PREMIUM. 9-26-18 CANCELLED - WAS $6803 |  |  | 9-21 done
51660-1 | MEDLINE 18720 | CAM LOCK TAP SECTION | AMERICAN ELECTRIC | 15231 | 2018-09-06 | 2018-09-28 |  | 2018-09-12 | done | 2018-05-30: mz 9-17 |  | PREMIUM - HOT HOT HOT SHIPPED 9-28-18
51643-1 -2 -3 | 17650 SOLARIS TI | DIST SECS, CABLE LANDING | AMERICAN ELECTRIC | 64039 | 2018-08-14 | 2018-09-28 |  | 2018-08-24 | Sie due 10-11. | 2018-05-30: 8-31 am doneish |  | GREGG; SHIP 6-8 WKS; IMMEDIATE RELEASE; add to GE swbrds; SHIPPED 9-28-18 | RS |  | 2018-08-24
51674-1 | HEB SA-41 SAN ANTONIO | ATS 2000-2000 | ERE | 44880 | 2018-09-20 | [11 empty] | SUBS 4 WKS - CANCELLED 9-27-18 REPLACED WITH 51683 |  |  | DUE 10-18
R510852 | HEB 028 | HEAT MOD KIT Complete kit | ERE |  |  | 2018-09-21 |  | 2018-09-13 | [8 empty] | SHIPPED 9-28-18
R512957 | BUC 40 KATY | HEAT KIT SIDE | ERE |  |  | 2018-09-21 |  | 2018-09-13 | [8 empty] | SHIPPED 9-228-18
R508513A | HEB 614 | HEAT KIT SIDE complete kit | ERE |  |  | 2018-09-21 |  | 2018-09-13 | [8 empty] | SHIPPED 9-28-18
R510858 | HEB 656 | HEAT KIT SIDE | ERE |  |  | 2018-09-27 | [10 empty] | SHIPPED 9-28-18
R512951 | BUC 30 WHARTON | HEAT KIT SIDE | ERE |  |  | 2018-09-27 | [10 empty] | SHIPPED 9-28-18
51667-1 | ROCHKIND | 800A SES MTR-MAIN W DIST | GEXPRO - LAS VEGAS | 11792 | 2018-09-13 | 2018-09-27 |  | 2018-09-14 | [8 empty] | PREMIUM - ESPI SHIPPED 9-28-18 |  |  | 2018-09-14
51651-1 | HMC ASHLEYS REDLANDS | DIST 2000A ADD TO 50343-2 4000A CROSS BUS | MAIN-SANTA ANA | 5225 | 2018-08-27 | 2018-09-27 | 20 | 2018-08-29 | INSULATORS | 2018-05-30: 9-6 mz |  | IMMEDIATE RELEASE; FUSIBLE SWITCHES - shipped 10-1-18
51654-1 | GOLDEN PALMS GARAGE | 600A SES N3R DIST GE BKRS | GEXPRO-LAS VEGAS | 12312 | 2018-08-30 | 2018-09-28 | 145 | 2018-09-07 | INSULATORS | 2018-05-30: 9-18 |  | ESPI - 4 week ship! Shipped 10-1-18 | RS |  | 9-11-18